## Sheet1
cat index | timeline index | Category | Sub-Category | Initiative | Barrier Description | Timeline | ID | Location Identified | Filtering-Contributors-Categories | Ease of Implementation | Impact (out of 10) | Metrics | Scope of Implementation | Preqrequisite initiative (s) | owner | contributors | sorting col 1 | sorting col 2 | Old ID
1 | 1 | Financing and Insurance | Access to Financing | Create and share a lending brief with private investors (banks, large REIT) and institutional investors in the region and outside Atlantic Canada to improve lender understanding of financing options and expand mortgage options. | Banks and lenders do not fully understand or accept modular/off-site construction because of high perceived risks in OSC (Atlantic). Limited financing options for small-scale ownership (e.g., single units, duplexes) force many buyers to rely on high-interest lenders (Atlantic). Financing rules, mortgage products, and banking policies are outdated for OSC (Atlantic). Lack of competition among funding providers (NS). | 2026 | FI1 | Atlantic, NS | Provincial Government, Finance & Insurance/Business Services, Federal Government | Easy | 8 | Number of lenders adopting the brief Reduction in financing rejections for modular Increase in modular mortgage approvals Reduced reliance on one or two banks Increase in competitive interest rates for modular | Regional | Gather modular timeline + risk data from manufacturers | Provincial Government, Finance & Insurance/Business Services | Federal Government, Finance & Insurance/Business Services | FI | 1 | FI1
2 | 4 | Financing and Insurance | Cost Structure | Introduce a OSC supplier pre-qualification pathway based on the factory’s CSA certification. | Bonding challenges for small manufacturers (NS, NB). | 2026 | FI4 | NS, NB | Manufacturers, Provincial Government, Finance & Insurance/Business Services | Medium | 8 | Number of modular tenders allowing pre-qualified suppliers without full bonding Increase in bid participation Reduced project cancellations due to lack of bonded bidders | Provincial | Define modular-specific qualification criteria Review manufacturer QA, capacity, and safety documentation | Provincial Government | Manufacturers, Finance & Insurance/Business Services | FI | 4 | FI8
3 | 5 | Financing and Insurance | Access to CMHC Funding | Collaborate with CMHC to establish a CMHC–regional coordination group. | CMHC policies do not align with OSC timelines, delivery methods, or cost structure (Atlantic). Restrictions on funding non-residential space in new buildings (Atlantic). Lack of clarity on how to access CMHC programs and funding streams (Atlantic). CMHC data for rural areas is outdated/incorrect (Atlantic). | 2026 | FI5 | Atlantic | Federal Government, Developers & General Contractors, Finance & Insurance/Business Services, Technical Professionals, Provincial Government | Medium | 9 | Reduced CMHC approval time for modular files Increase in successful modular applications | Regional | Collect standard modular factory timelines from local manufacturers Compare with CMHC approval timelines Identify specific misalignment points Draft modular timeline recommendations | Provincial Government, Federal Government | Developers & General Contractors, Technical Professionals, Finance & Insurance/Business Services | FI | 5 | FI9
4 | 6 | Financing and Insurance | Insurance | Work with the insurance sector to develop a unified OSC insurance model with clear liability transfer. | There are coverage gaps, overlapping insurance requirements, and unclear responsibility transfers between the factory, transporter, and on-site contractor (Atlantic). Higher insurance premiums for mass timber or wood-based modular systems (Atlantic). Insurance regulations not tailored to offsite fabrication risks (Atlantic). | 2026 | FI6 | Atlantic | Manufacturers, Transportation & Logistics Providers, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | Medium | 9 | Number of modular projects using wrap-up all-risk coverage Reduction in duplicated premiums Fewer liability disputes Warranty acceptance rate for modular modules Lower overall insurance cost per unit | Regional | Manufacturers + developers jointly approach insurance brokers Brokers prepare integrated wrap-up policy options Legal teams insert handover protocol clauses into modular contracts | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | Manufacturers, Federal Government, Developers & General Contractors, Transportation & Logistics Providers, Finance & Insurance/Business Services | FI | 6 | FI13
8 | 7 | Procurement Models and Contracts | Competition and Market Dynamics | Create a funding stream (through Opportunities NB, Invest NS, Innovation PEI and NL’s department of IET) for manufacturers to access and become CSA certified. | Only few CSA-certified modular manufacturers, limiting competition, raising costs, and preventing suppliers from scaling confidently (Atlantic). | 2026 | PM1 | Atlantic | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | Easy | 9 | Increase in number of pre-qualified modular suppliers Reduction in average bid prices Number of projects receiving more than 1–2 bids | Regional | Compile list of CSA A277/A660-certified manufacturers in ON/QC Create modular-specific pre-qualification criteria Issue pre-qualification call | Provincial Government | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | PM | 1 | PM1
9 | 8 | Procurement Models and Contracts | Competition and Market Dynamics | Use RFIs and RFQs to pre-qualify proponents, scoring them on KPIs beyond lowest bid. Include environment, social and culture KPIs in the proponent assessment process of an RFP. | Low-bid procurement models do not quantify the benefits of some forms of OSC (cost certainty, shortened schedule, reduction in environmental impact, safer for the skilled workforce) which makes OSC solutions less competitive than stick-built construction (Atlantic). Lack of value-based procurement approaches (Atlantic). | 2026 | PM2 | Atlantic | Developers & General Contractors, Manufacturers, Provincial Government, Federal Government, Municipal Government | Easy | 9 | Number of RFPs using separated cost line items Increase in modular bids submitted Reduction in modular bid disqualification due to upfront costs | Regional | Update procurement templates to require separated cost line items Provide short internal guidance to evaluators | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | PM | 2 | PM2
10 | 9 | Procurement Models and Contracts | Competition and Market Dynamics | Publish a rolling 3-4-year forecast of OSC-suitable (VMC or category 1 and panelized or category 2) public housing projects. | Unclear demand and supply conditions create a “chicken-or-egg” problem, limiting competition and complicating procurement planning (Atlantic). | 2026 | PM3 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | Easy | 9 | Number of modular projects included in forecast Manufacturer participation in bids Increase in factory expansion/production planning | Regional | Identify which upcoming public housing projects are modular-compatible Collect capital plans from municipalities + provinces | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | PM | 3 | PM3
11 | 10 | Procurement Models and Contracts | Competition and Market Dynamics | Use design–build procurement on projects that warrant a DB approach (e.g., >8 units). | Projects may need to be approved as design-build to create more competition (NS). | 2026 | PM4 | NS | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | Easy | 7 | Increase in number of modular bidders Reduction in redesign hours or change orders | Provincial | Identify modular-suitable projects early Issue RFPs using design–build method | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | PM | 4 | PM4
12 | 11 | Procurement Models and Contracts | Competition and Market Dynamics | Work with federal and provincial government to identify serviced or partially serviced small sites and combine to tender larger projects for one DB team. | Limited land availability reduces how many modular projects can be procured (NS). | 2026 | PM5 | NS | Provincial Government, Manufacturers, Technical Professionals, Municipal Government | Medium | 7 | Number of parcels identified and pre-cleared Number of parcels included in modular tenders Increase in modular-suitable land availability | Provincial | Inventory small provincial & municipal parcels Basic servicing and access assessments Municipal confirmation of allowable uses | Provincial Government | Manufacturers, Municipal Government, Technical Professionals | PM | 5 | PM5
13 | 12 | Procurement Models and Contracts | Design and Standards | Enable performance-based criteria. | Lack of OSC-friendly designs and prescriptive requirements cause redesign, inefficiencies, and excludes OSC methods (Atlantic). | 2026 | PM6 | Atlantic | Manufacturers, Developers & General Contractors, Provincial Government | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors | PM | 6 | PM6
14 | 13 | Procurement Models and Contracts | Design and Standards | Include an OSC integrator or experienced GC/CM as part of the project team early in the design phase to support OSC feasibility assessments and coordinate project timelines, including alignment with utility providers and other suppliers. | Designs are developed for traditional construction and only adapted to OSC methods later which causes redesign and inefficiencies (Atlantic). | 2026 | PM7 | Atlantic | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | Medium | 9 | Fewer redesign hours Reduction in change orders Number of projects identifying modular feasibility early | Regional | Early design teams receive modular design parameters (grid, module sizes, MEP zones) Consultation with manufacturers during concept design Include modular feasibility as a required step in RFP scopes | Provincial Government, Technical Professionals | Manufacturers, Developers & General Contractors, Technical Professionals | PM | 7 | PM7
15 | 14 | Financing and Insurance | Cost Structure | Add OSC-friendly payment frameworks and liquidity supports. | High upfront costs and misaligned payment milestones strain cash flow (Atlantic). | 2026 | PM8 | Atlantic | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | Medium | 9 | Number of RFPs using performance-based criteria Reduction in redesign hours Fewer modular bids rejected due to prescriptive design conflicts Increase in modular participation in tenders | Regional | Update design scopes to remove prescriptive structural and layout requirements Provide architects a set of modular design parameters (module sizes, grid, spans) Include modular considerations during concept/schematic design stages | Provincial Government, Technical Professionals | Manufacturers, Developers & General Contractors, Technical Professionals | PM | 8 | PM8
16 | 15 | Procurement Models and Contracts | Design and Standards | Ensure CSA A277 certification and emphasize the importance of the builds needing to meet building code of final building location. | Modular builds from other regions may not be designed to meet local performance standards (e.g., hurricane-force winds) (NS, NL). | 2026 | PM9 | NL, NS | Provincial Government, Technical Professionals, Manufacturers, Finance & Insurance/Business Services | Easy | 9 | Reduction in redesign requests post-award Number of proposals with compliant stamped engineering | Provincial | Add requirement for stamped structural verification in all modular RFPs Provide bidders with local wind/snow/climate indices Require early coordination with Atlantic-licensed engineers | Provincial Government | Manufacturers, Technical Professionals, Finance & Insurance/Business Services | PM | 9 | PM9
17 | 16 | Procurement Models and Contracts | Procurement Processes | Encourage tenders to use OSC alternatives. | Procurement is oriented toward traditional construction reducing acceptance for OSC approaches (Atlantic). | 2026 | PM10 | Atlantic | Provincial Government, Manufacturers, Municipal Government, Developers & General Contractors | Easy | 8 | Number of tenders allowing modular alternatives Number of modular alternative submissions | Regional | Add optional modular submission line to tender documents Provide evaluators guidance on comparing modular vs traditional approaches | Provincial Government, Municipal Government | Manufacturers, Developers & General Contractors, Municipal Government | PM | 10 | PM10
18 | 17 | Procurement Models and Contracts | Procurement Processes | Create consistent RFP processes across the four provinces and provide an FAQ and training session annually. | New entrants to construction are not used to RFP processes (NB). | 2026 | PM11 | NB | Manufacturers, Developers & General Contractors, Provincial Government | Easy | 7 | Reduction in incomplete modular submissions Increase in number of modular bidders Fewer administrative RFIs | Provincial | Identify common missing/incorrect items in past submissions | Provincial Government | Manufacturers, Developers & General Contractors | PM | 11 | PM12
19 | 18 | Procurement Models and Contracts | Procurement Processes | Include clear schedule requirements in contracts and link payments to project signing, factory-based project progress, delivery and installation milestones. | Lack of schedule regulations and enforcements (NB, PEI). | 2026 | PM12 | NB, PEI | Provincial Government, Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Easy | 9 | Number of tenders including schedule enforcement Reduction in installation or delivery delays | Provincial, regional | Identify modular-specific scheduling needs Update contract templates to include enforceable schedule milestones | Provincial Government, Municipal Government | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers | PM | 12 | PM14
20 | 19 | Procurement Models and Contracts | Design and Standards | Enable performance-based criteria. | Lack of flexible RFP formats - they are too structured and project specific (NB). | 2026 | PM13 | NB | Provincial Government, Manufacturers, Technical Professionals, Developers & General Contractors | Easy | 8 | Number of RFPs using performance-based requirements Increase in modular submissions Reduction in redesign/change-order costs | Provincial | Identify which requirements can be performance-based instead of prescriptive Train evaluators on comparing modular proposals Update RFP templates to include flexible requirements | Provincial Government | Manufacturers, Developers & General Contractors, Technical Professionals | PM | 13 | PM15
21 | 20 | Procurement Models and Contracts | Procurement Processes | Define OSC-specific responsibilities in trade scopes and use a standardized site-readiness checklist. | Pre-fabrication work is often missing from trade agreements and scopes, making coordination harder (Atlantic). | 2026 | PM14 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors, Technical Professionals | Medium | 8 | Fewer installation delays due to unclear responsibilities | Regional | Review typical modular scope boundaries (factory vs. on-site) Identify common interface failures on past projects Update procurement templates with modular-specific scope language | Provincial Government | Manufacturers, Developers & General Contractors, Technical Professionals | PM | 14 | PM16
22 | 21 | Procurement Models and Contracts | Manufacturing and Supply Chain | Issue bundled OSC procurement approaches (e.g., offtake agreements) to de-risk capacity investment in the regional manufacturers and add regional logistics supports. | Limited OSC manufacturing capacity and an under-developed supply chain create dependency on imports, transport bottlenecks, and long lead times (Atlantic). | 2026 | PM15 | Atlantic | Manufacturers, Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Finance & Insurance/Business Services, Municipal Government | Medium | 9 | Number of sites included in bundled procurements Factory production allocated to Atlantic projects Reduction in transport delays | Regional |  | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers, Finance & Insurance/Business Services | PM | 15 | PM17
23 | 22 | Procurement Models and Contracts | Design and Standards | Include an OSC integrator or experienced GC/CM as part of the project team early in the design phase to support OSC feasibility assessments and coordinate project timelines, including alignment with utility providers and other suppliers. | Designs are developed for traditional construction and only adapted to OSC methods later which causes redesign and inefficiencies (Atlantic). The timing for servicing and installing utilities like water, power and gas is uncertain (NB). | 2026 | PM16 | NB, Atlantic | Manufacturers, Developers & General Contractors, Provincial Government, Municipal Government, Transportation & Logistics Providers | Medium | 8 | Number of tenders with confirmed servicing dates Reduction in installation delays caused by utilities | Provincial | Early coordination meeting with utility providers Confirm servicing capacity and timelines | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers | PM | 16 | PM18
26 | 23 | Policy and Regulatory | Attitudes and Knowledge Gaps | Adopt the MMC Definition Framework across provincial and municipal policies, procurement documents and contracts. | Lack of alignment in terminology from funders. Ambiguity in terminology leading to confusion (NB). | 2026 | PR1 | NB | Municipal Government, Provincial Government, Federal Government, Manufacturers, Developers & General Contractors | Easy | 7 | Number of municipalities adopting the terminology Reduction in terminology-related rejections Consistency in NB Housing program applications | Local, provincial | Drafting of a concise modular terminology list based on CSA standards. Internal review by NB Housing, DLGLR, and municipal planners to confirm usability. Development of a short implementation memo instructing municipalities to adopt the terminology. | Provincial Government | Provincial Government, Manufacturers, Federal Government, Developers & General Contractors, Municipal Government | PR | 1 | PR2
27 | 24 | Policy and Regulatory | Attitudes and Knowledge Gaps | Develop an NB Healthy Housing Planning Note linking housing and year-round safe employment to population health. | Lack of emphasis of the impact of housing on population health (NB). | 2026 | PR2 | NB | Municipal Government, Provincial Government | Easy | 6 | Number of planning decisions referencing the Note. | Provincial | Drafting of the Healthy Housing Planning Note by NB Public Health with input from planning staff. Review and approval by DLGLR for integration into municipal planning processes. Distribution and short briefing session for development officers and planning commissions. | Provincial Government | Provincial Government, Municipal Government | PR | 2 | PR3
28 | 25 | Policy and Regulatory | Government Coordination | Establish the Atlantic Off-site Housing Innovation Network with a clear mandate including monthly (or quarterly inter-provincial meetings) with up to two points-of-contact reporting back to provincial committees. | Lack of communication across government agencies (Atlantic). | 2026 | PR3 | Atlantic | Provincial Government, Municipal Government, Manufacturers, Federal Government | Easy | 8 | Number of coordination meetings held Number of cross-department issues resolved Feedback from departments on clarity of roles | Regional | Identify representatives from Housing, Planning, Code, and Procurement in each province. Agree on basic Terms of Reference (purpose: modular-related coordination only). Create a shared information template for departments to submit updates/issues. Schedule quarterly virtual meetings (Atlantic-wide). | Provincial Government | Manufacturers, Federal Government, Municipal Government | PR | 3 | PR6
29 | 26 | Policy and Regulatory | Government Coordination | Designate a VMC Liaison Officer in NL. | Outdated policies needing to be updated (NL). | 2026 | PR4 | NL | Provincial Government, Technical Professionals, Municipal Government | Easy | 7 | Number of modular projects supported by the liaison Reduction in RFI volume related to outdated policies Faster issue resolution times (before vs after designation) Reduction in approval delays | Provincial | Assign an existing staff member in Service NL as Modular Liaison Officer (no new hiring needed). Establish mandate: resolve outdated-policy conflicts, coordinate with NL Housing, guide modular projects. Set up an intake channel like email or form for modular-related questions. Hold initial coordination meetings with NL Housing and priority municipalities. Start tracking outdated policies to inform future modernization efforts. | Provincial Government | Provincial Government, Municipal Government, Technical Professionals | PR | 4 | PR7
30 | 27 | Policy and Regulatory | Inspections | Involve an OSC integrator or mature GC/CM in projects >8 units to support on- and off-site coordination. | Operational complexity with OSC due to multiple contractors and on-site and off-site teams (NS). | 2026 | PR5 | NS | Provincial Government, Technical Professionals | Medium | 8 | Reduction in coordination issues reported. Reduction in duplicated site activities or installation delays Faster turnaround for modular installation scheduling Number of municipalities using it. Feedback from contractors and building officials on clarity | Provincial | Map existing modular workflows (factory → transport → installation → municipal inspection → site finishing). Identify common coordination problems across NS municipalities. Draft a unified workflow, responsibility matrix, and communication sequence. Engage NS Building Officials Association and municipalities for review. Pilot the protocol on 1–2 NSPHA modular projects and refine. Roll out province-wide through municipal channels and inspector associations. | Provincial Government | Technical Professionals | PR | 5 | PR8
31 | 28 | Policy and Regulatory | Permitting and Approvals | Undertake a review of by-laws to minimize the impact on OSC designed buildings and increase housing supply in the municipality. | Municipal zoning rules restrict certain housing types, proximity requirements, or have unclear procedures between zoning and permitting steps (Atlantic). | 2026 | PR6 | Atlantic | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | Easy | 9 | Improved clarity in pre-application reviews | Local, provincial, regional | Review existing zoning categories across sample municipalities. Identify where modular fits (e.g., single-unit, multi-unit, accessory). Validate with municipal planners and development officers. | Provincial Government, Municipal Government | Developers & General Contractors, Municipal Government, Technical Professionals | PR | 6 | PR13
32 | 29 | Policy and Regulatory | Permitting and Approvals | Create and publish a guide and then digitize the processes provide clarity to individuals involved in the approval process and all builders looking to build in the municipality. | Unclear processes: multiple layers of government or departments involved, unclear distinctions/responsibilities between codes, bylaws, and approval pathways (Atlantic). | 2026 | PR7 | Atlantic | Provincial Government, Municipal Government, Manufacturers, Developers & General Contractors | Easy | 9 | Reduction in process-related RFIs for modular files | Local, provincial, regional | Review current approval steps across select municipalities. Define departmental roles and responsibilities clearly. Draft the Approval Pathway section and integrate it into the PR4 Navigation Guide. Validate with municipal planners and building officials. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | PR | 7 | PR14
33 | 30 | Policy and Regulatory | Permitting and Approvals | Encourage the use of panelized (category 2) or other forms of OSC that can meet requirements within the Heritage Conservation Act. | Heritage Conservation Act identifies heritage places in unincorporated areas, providing a barrier for housing (NB). | 2026 | PR8 | NB | Provincial Government, Developers & General Contractors, Technical Professionals | Easy | 7 | Reduction in unplanned heritage-related delays Fewer RFIs to the Heritage Branch | Provincial | Confirm which heritage triggers apply in unincorporated areas Summarize permit types (site alteration, impact assessment) Draft short guidance text for Navigation Guide Validate with NB Heritage Branch | Provincial Government | Provincial Government, Developers & General Contractors, Technical Professionals | PR | 8 | PR15
40 | 31 | Transportation and Logistics | Module size and road restrictions | Collaborate across the region to develop overload escort/ permit requirements for both urban and rural centres to eliminate confusion across the sector. | Escort and permit rules for oversized modules (often >12 ft wide) differ between jurisdictions (Atlantic). | 2026 | TL1 | Atlantic | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Medium | 9 | Number of agreements signed Reduced delays due to permit harmonization Number of municipalities participating | Local, provincial, regional | Regulatory coordination between provinces Legal framework for transport agreements | Provincial Government, Municipal Government | Provincial Government, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers | TL | 1 | TL1
41 | 32 | Transportation and Logistics | Damage and Protection | Work with CCDC to create contract templates which identify roles and responsibilities of all parties and how project conflicts (module or panel damage) will be rectified. | Responsibility/liability for damage is unclear between manufacturer, hauler, GC (Atlantic). | 2026 | TL2 | Atlantic | Industry Associations, Developers & General Contractors, Transportation & Logistics Providers, Manufacturers, Finance & Insurance/Business Services | Easy | 7 | Reduction in disputes | Local | Development of formal insurance and liability agreements Stakeholder alignment | Industry Associations, Finance & Insurance/Business Services | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Industry Associations | TL | 2 | TL11
42 | 33 | Transportation and Logistics | Site access and Storage constraints | Create designated transportation routes with temporary staging yards for critical projects. | Limited staging and storage space near construction sites (Atlantic). Seasonal weight restrictions affecting transportation timelines (Atlantic). Difficult access in dense urban areas (tight roads, overhead utilities) (NS). | 2026 | TL3 | Atlantic, NS | Provincial Government, Academic/Training Institutions, Industry Associations | Difficult | 8 | Number of staging yards designated Reduction in delivery delays Improvement in on-time module deliveries | Local, provincial | Database of land potentiall available for staging near sites | Provincial Government | Provincial Government, Municipal Government, Transportation & Logistics Providers | TL | 3 | Tl14
51 | 35 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Collaborate across Atlantic post-secondary institutions to integrate OSC/MMC training through updating curricula, offering micro-credentials, workshops, or other training opportunities (e.g. AMC certificate). | NSCC programs closing due to low enrollment (NS). Few contractors have OSC experience, limiting participation (NS). | 2026 | WD1 | NS | Academic/Training Institutions, Provincial Government | Medium | 9 | Enrollment numbers in NSCC modular courses Campaign reach (social media, schools) Number of applications received | Local. provincial | Marketing campaign materials Coordination with NSCC and provincial education authorities | Provincial Government, Academic/Training Institutions | Academic/Training Institutions | WD | 1 | WD4
52 | 36 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Create streamlined credential-recognition pathways for internationally trained workers and consult with Indigenous communities to understand how to best overcome the barrier. | Barriers for foreign-trained workers to gain equivalency; limited culturally appropriate programs for Indigenous communities (NS). | 2026 | WD2 | NS | Industry Associations, Indigenous & Community Organizations, Provincial Government, Academic/Training Institutions | Medium | 8 | Number of foreign-trained workers completing recognition process Number of culturally appropriate programs delivered Participation by Indigenous students | Provincial, regional | Agreements with credentialing bodies Partnerships with Indigenous organizations Development of training content | Provincial Government | Industry Associations, Academic/Training Institutions, Indigenous & Community Organizations | WD | 2 | WD5
53 | 37 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Promote collaboration and include heavy equipment and crane operations in the outreach for opportunities in the industry. | Limited access to specialized equipment operators (e.g., cranes, certified operators) (Atlantic). | 2026 | WD3 | Atlantic | Industry Associations, Transportation & Logistics Providers, Provincial Government | Difficult | 8 | Counts of shared resources Project delays due to lack of resources | Regional | Coordination agreements between provinces Identification of regional capacity gaps | Provincial Government, Federal Government | Federal Government, Transportation & Logistics Providers, Industry Associations | WD | 3 | WD9
54 | 38 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Improve scheduling efficiency. | Noise and work-hour limits reduce labour availability (NS). | 2026 | WD4 | NS | Manufacturers, Municipal Government | Easy | 6 | Compliance with noise scheduling Reduced labour downtime | Local | Development of optimized scheduling guidelines Coordination with local municipalities | Manufacturers, Municipal Government | Manufacturers | WD | 4 | WD13
55 | 39 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability |  | Lack of on-island OSC experts on off-site methods (PEI) | 2026 | WD5 | PEI | Provincial Government, Industry Associations | Easy | 8 | Number of training sessions hosted Number of attendees trained | Provincial | Workshop scheduling and content planning | Provincial Government | Industry Associations | WD | 5 | WD14
56 | 40 | Skilled workforce and Skills Development | Awareness, Culture & Mindset | Host OSC industry events (tours, seminars, etc.) targeting skilled trades to highlight OSC and associated benefits. | Workforce resistance to OSC due to lack of familiarity, fear of job loss, or cultural hesitation toward new methods (Atlantic). | 2026 | WD6 | Atlantic | Provincial Government, Industry Associations | Easy | 8 | Attendance at OSC events Surveys on workforce perception of OSC Increased modular adoption | Regional, provincial | Identification of industry professionals to host events Event planning | Provincial Government | Industry Associations | WD | 6 | WD15
5 | 41 | Financing and Insurance | Cost Structure | Educate the supply chain and develop an OSC cost library with standardized cost ranges (e.g., RS Means). | Challenges producing accurate pricing estimates due to immature market (Atlantic). | 2027 | FI7 | Atlantic | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | FI | 7 | FI6
6 | 42 | Financing and Insurance | Cost Structure | Use existing MURB VMC projects as a case study to identify cost reductions or work with all forms of OSC to determine the best approach to buildings MURBs on PEI. | Multi-unit residential building (MURB) volumetric modular construction significantly more expensive (PEI). | 2027 | FI8 | PEI | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services, Transportation & Logistics Providers | Medium | 9 | Reduction in module transport cost Number of projects participating in shared logistics Increased adoption of modular for multi-unit builds | Provincial | Map annual modular demand (public + private) in PEI Identify suppliers shipping to PEI and shipment patterns Pre-negotiate ferry/logistics windows Pre-qualify crane + install contractors willing to participate Develop cost-sharing model among participating projects | Provincial Government | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Finance & Insurance/Business Services | FI | 8 | FI7
7 | 43 | Financing and Insurance | Incentives & Policy | Establish a pre-manufactured OSC index, with associated fee reductions and expedited approvals for pre-verified OSC designs. | No tax incentives, subsidies, or financial supports tailored to OSC (Atlantic). Government fees add affordability challenges (Atlantic). | 2027 | FI9 | Atlantic | Manufacturers, Provincial Government, Federal Government, Indigenous & Community Organizations, Developers & General Contractors | Medium | 8 | Number of modular units delivered under the credit Reduction in per-unit cost for provincial housing builds Increase in manufacturer production volume | Provincial, regional | Determine per-unit credit value (e.g., $2,000–$5,000/unit) Set eligibility (affordable housing, supportive housing, repeatable modular designs) Secure small annual budget allocation Develop simple claim process at delivery or installation | Provincial Government | Manufacturers, Federal Government, Developers & General Contractors, Indigenous & Community Organizations | FI | 9 | FI16
34 | 44 | Policy and Regulatory | Attitudes and Knowledge Gaps | Support the public and private sector in education and create a regional OSC approval pathway supported by coordinated public-awareness program. | There is a gap between the promotion of OSC and the acceptance of it. Specifically, politicians have been promoting OSC however their departments do not prefer it. A gap was also noted in CMHC promoting OSC despite the funding mechanisms not being friendly to OSC (Atlantic). | 2027 | PR9 | Atlantic | Municipal Government, Provincial Government, Federal Government, Manufacturers | Medium | 9 | Number of projects approved Approval time Number of departments using pathway | Regional | Development of clear eligibility criteria for selecting modular demonstration projects. Creation of a standardized modular submission package for applicants. Preparation of a modular review checklist for inspectors and permitting staff. | Provincial Government | Manufacturers, Federal Government, Municipal Government | PR | 9 | PR1
35 | 45 | Policy and Regulatory | Codes and Standards | At a regional level, work with the NRC to create a technical committee to update the code for OSC and educate planners, architects, building officials and relevant industry members. | Complexity of codes: mention of challenges navigating national, provincial, and local codes (including NBC, NECB) (Atlantic). | 2027 | PR10 | Atlantic | Provincial Government, Technical Professionals, Manufacturers | Medium | 8 | Change in average permit review times for modular projects (before vs after guide) Number of municipalities that formally adopt or reference the AM-CNG in procedures Number of RFIs or code-related clarifications requested on modular submissions (aim: decrease) Number of building officials / plan reviewers trained using the guide | Regional | Inventory of existing modular-related code interpretations and issues Inventory of existing modular-related code interpretations and issues Draft modular-specific code navigation guide for review Pilot the guide with a small set of municipalities / projects | Provincial Government | Manufacturers, Technical Professionals | PR | 10 | PR4
36 | 46 | Policy and Regulatory | Inspections | Standardize and promote CSA A277 adoption across all municipalities through aligned policy, consistent inspection practices, targeted inspector education, and certification incentives. | Concerns about duplicate inspections resulting in inefficiencies (Atlantic) | 2027 | PR11 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors | Medium | 9 | Reduction in duplicated inspection steps % of Atlantic municipalities using the acceptance framework Shortened inspection timelines for modular projects Fewer RFI (Requests for Information) from inspectors Improved manufacturer feedback on municipal acceptance | Regional | Map which inspections are already covered under CSA A277 (factory QA, structural, plumbing rough-ins, electrical pre-wiring, firestopping inside modules). List which inspections MUST remain on-site (foundation, hookups, sealing, fire separations, assembly). Review differences in inspection practices across Atlantic municipalities. Draft the shared Framework | Provincial Government | Manufacturers, Developers & General Contractors | PR | 11 | PR9
37 | 47 | Policy and Regulatory | Inspections | Standardize and promote CSA A277 adoption across all municipalities through aligned policy, consistent inspection practices, targeted inspector education, and certification incentives. | Cost barriers and lack of incentives to becoming CSA certified (NL). | 2027 | PR12 | NL | Provincial Government, Manufacturers | Medium | 8 | Number of manufacturers receiving rebate Number of manufacturers getting CSA certification Increase in modular supply in NL | Provincial | Define the rebate criteria, including which manufacturers are eligible and what conditions must be met. Confirm which certification costs are eligible. Set up a simple application form so manufacturers can submit proof of certification to receive the rebate. | Provincial Government | Provincial Government, Manufacturers | PR | 12 | PR10
38 | 48 | Policy and Regulatory | Permitting and Approvals | Use design catalogues, such as the CMHC Housing Design Catalogue or develop municipality-specific design catalogues, to pre-approve permitting for projects built according to the catalogue designs. | Slow and costly approval processes (Atlantic). | 2027 | PR13 | Atlantic | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | Medium | 9 | Average modular permitting time before vs. after track Number of repeatable modular designs pre-verified Increase in modular applications submitted | Local, provincial | Identify which modular designs can be pre-verified. Provide municipalities with CSA certification details. Update municipal workflows to skip factory-completed checks. | Provincial Government, Municipal Government | Developers & General Contractors, Municipal Government, Technical Professionals | PR | 13 | PR12
39 | 49 | Policy and Regulatory | Inspections | Standardize and promote CSA A277 adoption across all municipalities through aligned policy, consistent inspection practices, targeted inspector education, and certification incentives. | Concerns that inspections done on components in factory instead of the whole building could lead to hidden issues which may emerge when components are combined (NS). Challenges related to codes and standards differing between provinces and municipalities. In addition to accessibility codes and seismic requirements differing across the country (NS). | 2027 | PR14 | Atlantic | [8 empty] | PR | 14 | PR5
43 | 50 | Transportation and Logistics | Module size and road restrictions | Consider design for manufacturing, transportation and assembly by province with the provinces transportation constraints in mind. | Module width/height is constrained by bridge clearances, turning radii, and road widths (Atlantic). Modules must be designed to match available island transport equipment (NL). | 2027 | TL5 | Atlantic, NL | Provincial Government, Technical Professionals, Manufacturers | Medium | 7 | Data collected on road restrictions Number of transportation-friendly designs used | Provincial, local | Data collection on bridges, roads, turning radii Mapping infrastructure conflicts Design catalogue development Coordination between designers, manufacturers, transport providers | Provincial Government, Manufacturers | Provincial Government, Technical Professionals, Manufacturers | TL | 5 | Tl2
44 | 51 | Transportation and Logistics | Module size and road restrictions | Develop a pre-approved OSC route and work with ferry companies to provide discounted or off-peak ferry rates for projects carrying critical infrastructure (e.g., affordable housing). | Ferry costs add major expense for panelized construction (NL). | 2027 | TL6 | NL | Provincial Government, Transportation & Logistics Providers | Easy | 8 | Number of ferry trips using discounted/off-peak rates Cost savings On-time deliveries | Provincial | Agreements with ferry operators Approval of subsidy program | Provincial Government, Transportation & Logistics Providers | Provincial Government, Transportation & Logistics Providers | TL | 6 | TL5
45 | 52 | Transportation and Logistics | Module size and road restrictions | Work with NBDTI and local municipalities to consider OSC delivery on detour routes. | Poor detour roads increase delivery risk (NB). | 2027 | TL7 | NB | Provincial Government, Transportation & Logistics Providers | Difficult | 8 | Condition of delivery routes Reduced transport incidents Maintenance logs | Provincial | Identification of modular delivery routes Allocation of maintenance funding | Provincial Government, Transportation & Logistics Providers | Provincial Government, Transportation & Logistics Providers | TL | 7 | TL6
46 | 53 | Transportation and Logistics | Damage and Protection | Identify an OSC integrator role in the project team to ensure proper planning and location of heavy equipment for transportation, erection and installation. | Heavy machinery causes soil compaction and clearing (NS). | 2027 | TL8 | NS | Provincial Government, Transportation & Logistics Providers | Difficult | 8 | Condition of delivery routes Reduced transport incidents Maintenance logs | Provincial | Identification of modular delivery routes Allocation of maintenance funding | Provincial Government, Transportation & Logistics Providers | Provincial Government, Transportation & Logistics Providers | TL | 8 | TL13
47 | 54 | Transportation and Logistics | Module size and road restrictions | Consider design for manufacturing, transportation and assembly by province with the provinces transportation constraints in mind. | No standardized dimensions for local volumetric modular practice (NS). | 2027 | TL9 | NS | Industry Associations, Provincial Government, Municipal Government, Municipal Government | Medium | 9 | Pre-approved design adoption Reduced transport-related issues | Local, regional, national | Development of standard modular dimensions Coordination with local authorities | Provincial Government | Municipal Government, Industry Associations | TL | 9 | TL7
48 | 55 | Transportation and Logistics | Damage and Protection | In parallel, work with the HPBR Lab on R&D to eliminate damages during transportation, erection and assembly. | Denting, corner damage, and structural movement during loading/unloading (Atlantic). Inconsistent moisture barriers and wrapping practices (Atlantic). | 2027 | TL10 | Atlantic | Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Academic/Training Institutions, Industry Associations | Easy | 8 | Number of training sessions delivered Reports of damage to modules during transportation | National | Transport best-practice guidelines finalized Training content developed | Academic/Training Institutions | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Industry Associations, Academic/Training Institutions | TL | 10 | TL12
57 | 56 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Build off the AMC certificate to develop a national OSC curriculum and align apprenticeships with OSC credentials. | Lack of clear, unified training pathways or standards for OSC across Canada (Atlantic). | 2027 | WD7 | Atlantic | Industry Associations, Academic/Training Institutions | Medium | 8 | Adoption rate of national curriculum by provinces Number of institutions offering courses Enrollment numbers | National, provincial | Align provincial apprenticeship bodies to recognize modular-specific credentials Establish CHBA alignment Approval by national training authorities Funding for curriculum development | FALSE | Industry Associations, Academic/Training Institutions | WD | 7 | WD3
58 | 57 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Expand OSC-focused trade training, fast-track upskilling, and introduce industry-supported apprenticeships. | Shortage of skilled trades needed for OSC construction (design, assembly, mass timber, mechanical/electrical, etc.) (NB). | 2027 | WD8 | NB | Provincial Government, Academic/Training Institutions, Industry Associations | Easy | 8 | Number of apprenticeships created Program enrollment Industry placement rates | Regional | College/unions agreement Curriculum development Employer sponsorship secured | Provincial Government, Industry Associations, Academic/Training Institutions | Industry Associations, Academic/Training Institutions | WD | 8 | WD6
59 | 58 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Provide relocation incentives and additional benefits (e.g., housing) to grow the workforce. | Rural factory locations limit labour access and reduce available workforce pools (Atlantic). | 2027 | WD9 | Atlantic | Provincial Government, Manufacturers, Federal Government | Difficult | 7 | Number of relocation/housing subsidies granted Change in labour availability at rural facilities | Regional, local | Provincial/federal funding approval Policy design for incentives | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government | WD | 9 | WD8
60 | 59 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Identify training (e.g., AMC certificate) for existing municipal staff, increase staffing, digitize processes (e.g., permitting), and adopt pre-approved OSC designs. | Staff shortages in public offices (planning, permitting, fire inspection) delay projects (NB). New building inspectors are inexperienced (NL). | 2027 | WD10 | NB, NL | Municipal Government, Provincial Government, Academic/Training Institutions | Medium | 9 | Number of municipal staff hired Permitting turnaround times Number of inspectors trained Inspector certification rates Reduced inspection delays | Local, provincial | Budget approval Digital permitting system development Curriculum development for inspector training | Provincial Government, Academic/Training Institutions | Provincial Government, Federal Government, Municipal Government | WD | 10 | WD11
61 | 60 | Skilled workforce and Skills Development | Workforce Retention & Recruitment | With a commitment to OSC through offtake agreements, OSC businesses can offer long-term year-round employment and should consider full health and dental and additional benefits (subsidized housing, healthy living allowance, etc.) | Workforce retention challenges due to high living costs, housing affordability, and job security concerns in the construction sector (Atlantic). | 2027 | WD11 | Atlantic | Provincial Government, Manufacturers, Federal Government, Industry Associations | Difficult | 9 | Worker retention rates Housing uptake Employment stability metrics | Local, regional | Policy approval for housing subsidies Government purchasing agreements finalized | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | WD | 11 | WD18
49 | 61 | Transportation and Logistics | Module size and road restrictions | Collaborate across the region to compile and document jurisdiction-specific overload escort and permit requirements for urban and rural centres in a single reference document, to eliminate confusion across the sector. | Larger modules require police escorts; delays occur when escorts leave (NS). HRM has distinct escort/permit timing from rural NS (NS). | 2026-2027 | TL11 | NS | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Medium | 9 | Number of pre-approved routes Reduced police escort requirements Transport time savings | Local, provincial | Mapping of routes Coordination with police and municipal authorities | Provincial Government, Municipal Government | Provincial Government, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers | TL | 11 | TL9
50 | 62 | Transportation and Logistics | Module size and road restrictions | Identify OSC delivery routes and infrastructure conflict-point database and when favourable use alternate construction methods to volumetric modular. | Conflicts with power lines, telecommunications, and fire marshal requirements (NB). | 2026-2027 | TL12 | NB | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Medium | 7 | Number of conflicts identified in database Reduction in transport delays due to conflicts | Local, provincial | Database of infrastructure conflict points developed | Provincial Government | Developers & General Contractors, Municipal Government, Transportation & Logistics Providers | TL | 12 | TL15
62 | 63 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Collaborate across Atlantic post-secondary institutions to integrate OSC/MMC training through updating curricula, offering micro-credentials, workshops, or other training opportunities (e.g. AMC certificate). | NSCC programs closing due to low enrollment (NS). Retraining to shift workers from traditional methods to MMC (Atlantic). Lack of clear, unified training pathways or standards for OSC across Canada (Atlantic). Few OSC-specific training programs across colleges/trade schools (Atlantic). Lack of on-island OSC experts on off-site methods (PEI). | 2026-2027 | WD12 | Atlantic | Provincial Government, Academic/Training Institutions, Industry Associations | Easy | 7 | Number of participants completing mini-courses Number of certificates issued Employer satisfaction with trained workforce | Regional |  | Provincial Government, Industry Associations, Academic/Training Institutions | Provincial Government, Industry Associations, Academic/Training Institutions | WD | 12 | WD2
63 | 64 | Skilled workforce and Skills Development | Skilled Trades & Labour Availability | Invest in factory automation to increase supply and strengthen OSC recruitment. | Low overall workforce availability limits the ability to scale modular construction (Atlantic). | 2026-2027 | WD13 | Atlantic | Provincial Government, Industry Associations, Manufacturers, Federal Government | Medium | 9 | Efficiency KPIs folllowing implementation of automation Output per worker Reduced labour bottlenecks | Local, regional | Investment in automation equipment Worker training on new technology | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | WD | 13 | WD7
64 | 65 | Skilled workforce and Skills Development | Awareness, Culture & Mindset | Create a docuseries, launch an OSC awareness campaign, develop industry-wide marketing, and require outreach from publicly funded companies. | Low awareness and misconceptions about OSC quality, aesthetics, and durability (Atlantic). | 2026-2027 | WD14 | Atlantic | Provincial Government, Industry Associations, Manufacturers, Federal Government | Easy | 9 | Public awareness metrics (survey data) Number of facility open houses Participation in outreach | National, regional, provincial | Marketing strategy developed Local case studies collected Cooperation from manufacturers | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | WD | 14 | WD16
65 | 66 | Skilled workforce and Skills Development | Awareness, Culture & Mindset | Work with trade schools and associations to host OSC events, sponsor trades, and integrate OSC into existing programs. | Limited promotion of modular construction within the industry and workforce (Atlantic). | 2026-2027 | WD15 | Atlantic | Industry Associations, Industry Associations, Manufacturers, Academic/Training Institutions | Easy | 8 | Number of OSC events held Number of sponsorships awarded and recipient career paths Training integration into programs | Regional, provincial, maybe national | Event planning and secured funding for sponsorships | Provincial Government, Manufacturers, Academic/Training Institutions | Manufacturers, Industry Associations, Academic/Training Institutions | WD | 15 | WD17
66 | 67 | Skilled workforce and Skills Development | Workforce Retention & Recruitment | Highlight the benefits of OSC company employment (year-round shift work) and support with bursaries, scholarships, mentorships, and DEI training requirements. | Difficulty attracting youth, women, diverse groups, and newcomers to construction trades (Atlantic). | 2026-2027 | WD16 | Atlantic | Municipal Government, Provincial Government, Academic/Training Institutions, Manufacturers, Federal Government, Indigenous & Community Organizations | Medium | 9 | Scholarship uptake Mentorship participation Diversity metrics in workforce | Provincial, regional | Funding approval for scholarships Mentorship program structure | Provincial Government, Indigenous & Community Organizations | Provincial Government, Manufacturers, Federal Government, Municipal Government, Academic/Training Institutions | WD | 16 | WD19
67 | 68 | Skilled workforce and Skills Development | Workforce Retention & Recruitment | Consult with Indigenous communities to identify initiatives to overcome this barrier. | Culturally inappropriate or unwelcoming workplaces limit participation from Indigenous peoples and underrepresented groups (NB). | 2026-2027 | WD17 | NB | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | Easy | 8 | Number of Indigenous-owned businesses supported DEI training completion Workforce participation rates | Provincial, regional | Funding and program approval DEI curriculum developed | Provincial Government, Indigenous & Community Organizations | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | WD | 17 | WD20
24 | 69 | Procurement Models and Contracts | Competition and Market Dynamics | Develop a modular cost library with standardized cost ranges and typical modular inputs. | Lack defined roles and responsibilities leading to inaccurate pricing from sub-contractors (PEI) | 2026 -2028 | PM17 | PEI | Manufacturers, Developers & General Contractors, Provincial Government | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors | PM | 17 | PM6
25 | 70 | Procurement Models and Contracts | Procurement Processes | Include as much detail in the RFPs as possible (e.g., geotechnical report, potential laydown areas, potential overhead constraints, etc.) as well as images of the site to ensure proponents provide an accurate estimate. | Lack of site access or information for bidders to accurately estimate on-site works (NB). | 2026 -2028 | PM18 | NB | Manufacturers, Developers & General Contractors, Provincial Government | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors | PM | 18 | PM13