## Sheet1
Index | Category | Sub-Category | Initiative | Barrier Description | Timeline | ID | Location Identified | Filtering-Contributors-Categories | Ease of Implementation | Impact (out of 10) | Metrics | Scope of Implementation | Preqrequisite initiative (s) | owner | contributors | timeline-ordering | Independent vs Collaboration | NB Status | NS Status | PEI Status | NL Status | Regional | Metric Notes
1 | Financing and insurance | Cost Structure | Introduce MMC manufacturer pre-qualification based on CSA A277 certification. | Bonding challenges for small manufacturers (NS, NB). | 2026 | FI1 | NS, NB | Manufacturers, Provincial Government, Finance & Insurance/Business Services | Medium | 8 | Number of modular tenders allowing pre-qualified suppliers without full bonding Increase in bid participation Reduced project cancellations due to lack of bonded bidders | Provincial | Define modular-specific qualification criteria Review manufacturer QA, capacity, and safety documentation | Provincial Government | Manufacturers, Finance & Insurance/Business Services | 20262026 | Independent | Pending | Pending | Pending | Pending | -
2 | Financing and insurance | Access to CMHC Funding | Collaborate with CMHC to establish a CMHC–regional coordination group. | CMHC policies do not align with OSC timelines, delivery methods, or cost structure (Atlantic). Restrictions on funding non-residential space in new buildings (Atlantic). Lack of clarity on how to access CMHC programs and funding streams (Atlantic). CMHC data for rural areas is outdated/incorrect (Atlantic). | 2026 | FI2 | Atlantic | Federal Government, Developers & General Contractors, Finance & Insurance/Business Services, Technical Professionals, Provincial Government | Medium | 9 | Reduced CMHC approval time for modular files Increase in successful modular applications | Regional | Collect standard modular factory timelines from local manufacturers Compare with CMHC approval timelines Identify specific misalignment points Draft modular timeline recommendations | Provincial Government, Federal Government | Developers & General Contractors, Technical Professionals, Finance & Insurance/Business Services | 20262026 | Collaboration | - | - | - | - | Pending
3 | Financing and insurance | Access to Financing | Create and share lending briefs with private and institutional investors to expand financing options. | Banks and lenders do not fully understand or accept modular/off-site construction because of high perceived risks in OSC (Atlantic). Limited financing options for small-scale ownership (e.g., single units, duplexes) force many buyers to rely on high-interest lenders (Atlantic). Financing rules, mortgage products, and banking policies are outdated for OSC (Atlantic). Lack of competition among funding providers (NS). | 2026 | FI3 | Atlantic, NS | Provincial Government, Finance & Insurance/Business Services, Federal Government | Easy | 8 | Number of lenders adopting the brief Reduction in financing rejections for modular Increase in modular mortgage approvals Reduced reliance on one or two banks Increase in competitive interest rates for modular | Regional | Gather modular timeline + risk data from manufacturers | Provincial Government, Finance & Insurance/Business Services | Federal Government, Finance & Insurance/Business Services | 20262026 | Collaboration | - | - | - | - | Pending
4 | Financing and insurance | Cost Structure | Use MURB projects as case studies to identify cost reductions for MURBs that use MMC. | Multi-unit residential building (MURB) volumetric modular construction significantly more expensive (PEI). | 2027 | FI4 | PEI | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services, Transportation & Logistics Providers | Medium | 9 | Reduction in module transport cost Number of projects participating in shared logistics Increased adoption of modular for multi-unit builds | Provincial | Map annual modular demand (public + private) in PEI Identify suppliers shipping to PEI and shipment patterns Pre-negotiate ferry/logistics windows Pre-qualify crane + install contractors willing to participate Develop cost-sharing model among participating projects | Provincial Government | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Finance & Insurance/Business Services | 20272027 | Independent | Pending | Pending | Pending | Pending | -
5 | Financing and insurance | Cost Structure | Add MMC-friendly (particularly for categories 1 to 4) payment structures and liquidity supports. | High upfront costs and misaligned payment milestones strain cash flow (Atlantic). | 2026 | FI5 | Atlantic | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | Medium | 9 | Number of RFPs using performance-based criteria Reduction in redesign hours Fewer modular bids rejected due to prescriptive design conflicts Increase in modular participation in tenders | Regional | Update design scopes to remove prescriptive structural and layout requirements Provide architects a set of modular design parameters (module sizes, grid, spans) Include modular considerations during concept/schematic design stages | Provincial Government, Technical Professionals | Manufacturers, Developers & General Contractors, Technical Professionals | 20262026 | Collaboration | - | - | - | - | Pending
6 | Financing and insurance | Incentives & Policy | Establish a pre-manufactured index with fee reductions and expedited approvals. | No tax incentives, subsidies, or financial supports tailored to OSC (Atlantic). Government fees add affordability challenges (Atlantic). | 2027 | FI6 | Atlantic | Manufacturers, Provincial Government, Federal Government, Indigenous & Community Organizations, Developers & General Contractors | Medium | 8 | Number of modular units delivered under the credit Reduction in per-unit cost for provincial housing builds Increase in manufacturer production volume | Provincial, regional | Determine per-unit credit value (e.g., $2,000–$5,000/unit) Set eligibility (affordable housing, supportive housing, repeatable modular designs) Secure small annual budget allocation Develop simple claim process at delivery or installation | Provincial Government | Manufacturers, Federal Government, Developers & General Contractors, Indigenous & Community Organizations | 20272027 | Independent | Pending | Pending | Pending | Pending | -
7 | Financing and insurance | Insurance | Work with insurers to develop a unified OSC insurance products aligned with MMC (categories 1 to 4) with clear liability transfer. | There are coverage gaps, overlapping insurance requirements, and unclear responsibility transfers between the factory, transporter, and on-site contractor (Atlantic). Higher insurance premiums for mass timber or wood-based modular systems (Atlantic). Insurance regulations not tailored to offsite fabrication risks (Atlantic). | 2026 | FI7 | Atlantic | Manufacturers, Transportation & Logistics Providers, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | Medium | 9 | Number of modular projects using wrap-up all-risk coverage Reduction in duplicated premiums Fewer liability disputes Warranty acceptance rate for modular modules Lower overall insurance cost per unit | Regional | Manufacturers + developers jointly approach insurance brokers Brokers prepare integrated wrap-up policy options Legal teams insert handover protocol clauses into modular contracts | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | Manufacturers, Federal Government, Developers & General Contractors, Transportation & Logistics Providers, Finance & Insurance/Business Services | 20262026 | Collaboration | - | - | - | - | Pending
8 | Policy and regulatory | Attitudes and Knowledge Gaps | Adopt the MMC Definition Framework across government department and leverage the definitions in policies, procurement documents, and contracts. | Lack of alignment in terminology from funders. Ambiguity in terminology leading to confusion (NB). | 2026 | PR1 | NB | Municipal Government, Provincial Government, Federal Government, Manufacturers, Developers & General Contractors | Easy | 7 | Number of municipalities adopting the terminology Reduction in terminology-related rejections Consistency in NB Housing program applications | Local, provincial | Drafting of a concise modular terminology list based on CSA standards. Internal review by NB Housing, DLGLR, and municipal planners to confirm usability. Development of a short implementation memo instructing municipalities to adopt the terminology. | Provincial Government | Provincial Government, Manufacturers, Federal Government, Developers & General Contractors, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
9 | Policy and regulatory | Attitudes and Knowledge Gaps | Develop an NB Healthy Housing Planning Note linking housing and year-round safe employment to population health. | Lack of emphasis of the impact of housing on population health (NB). | 2026 | PR2 | NB | Municipal Government, Provincial Government | Easy | 6 | Number of planning decisions referencing the Note. | Provincial | Drafting of the Healthy Housing Planning Note by NB Public Health with input from planning staff. Review and approval by DLGLR for integration into municipal planning processes. Distribution and short briefing session for development officers and planning commissions. | Provincial Government | Provincial Government, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
10 | Policy and regulatory | Attitudes and Knowledge Gaps | Support public and private sector education and create a regional MMC approval pathway supported by awareness programs. | There is a gap between the promotion of OSC and the acceptance of it. Specifically, politicians have been promoting OSC however their departments do not prefer it. A gap was also noted in CMHC promoting OSC despite the funding mechanisms not being friendly to OSC (Atlantic). | 2027 | PR3 | Atlantic | Municipal Government, Provincial Government, Federal Government, Manufacturers | Medium | 9 | Number of projects approved Approval time Number of departments using pathway | Regional | Development of clear eligibility criteria for selecting modular demonstration projects. Creation of a standardized modular submission package for applicants. Preparation of a modular review checklist for inspectors and permitting staff. | Provincial Government | Manufacturers, Federal Government, Municipal Government | 20272027 | Independent | Pending | Pending | Pending | Pending | -
11 | Policy and regulatory | Codes and Standards | Work with NRC and the necessary codes, committees and commissions to establish a technical committee to update codes for MMC and educate planners and officials. | Complexity of codes: mention of challenges navigating national, provincial, and local codes (including NBC, NECB) (Atlantic). | 2027 | PR4 | Atlantic | Provincial Government, Technical Professionals, Manufacturers | Medium | 8 | Change in average permit review times for modular projects (before vs after guide) Number of municipalities that formally adopt or reference the AM-CNG in procedures Number of RFIs or code-related clarifications requested on modular submissions (aim: decrease) Number of building officials / plan reviewers trained using the guide | Regional | Inventory of existing modular-related code interpretations and issues Inventory of existing modular-related code interpretations and issues Draft modular-specific code navigation guide for review Pilot the guide with a small set of municipalities / projects | Provincial Government | Manufacturers, Technical Professionals | 20272027 | Collaboration | - | - | - | - | Pending
12 | Policy and regulatory | Government Coordination | Establish the Atlantic Off-site Housing Innovation Network with a clear mandate including monthly (or quarterly inter-provincial meetings) with up to two points-of-contact reporting back to provincial committees. | Lack of communication across government agencies (Atlantic). | 2026 | PR5 | Atlantic | Provincial Government, Municipal Government, Manufacturers, Federal Government | Easy | 8 | Number of coordination meetings held Number of cross-department issues resolved Feedback from departments on clarity of roles | Regional | Identify representatives from Housing, Planning, Code, and Procurement in each province. Agree on basic Terms of Reference (purpose: modular-related coordination only). Create a shared information template for departments to submit updates/issues. Schedule quarterly virtual meetings (Atlantic-wide). | Provincial Government | Manufacturers, Federal Government, Municipal Government | 20262026 | Collaboration | - | - | - | - | Pending
13 | Policy and regulatory | Government Coordination | Designate a MMC Liaison Officer in NL. This individual should ideally have expertise in traditional, panelized (category 2) and volumetric modular (category 1) construction. | Outdated policies needing to be updated (NL). | 2026 | PR6 | NL | Provincial Government, Technical Professionals, Municipal Government | Easy | 7 | Number of modular projects supported by the liaison Reduction in RFI volume related to outdated policies Faster issue resolution times (before vs after designation) Reduction in approval delays | Provincial | Assign an existing staff member in Service NL as Modular Liaison Officer (no new hiring needed). Establish mandate: resolve outdated-policy conflicts, coordinate with NL Housing, guide modular projects. Set up an intake channel like email or form for modular-related questions. Hold initial coordination meetings with NL Housing and priority municipalities. Start tracking outdated policies to inform future modernization efforts. | Provincial Government | Provincial Government, Municipal Government, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
14 | Policy and regulatory | Inspections | Standardize and promote CSA A277 adoption across municipalities through aligned policy, inspection practices, and inspector training. | Concerns about duplicate inspections resulting in inefficiencies (Atlantic) | 2027 | PR7 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors | Medium | 9 | Reduction in duplicated inspection steps % of Atlantic municipalities using the acceptance framework Shortened inspection timelines for modular projects Fewer RFI (Requests for Information) from inspectors Improved manufacturer feedback on municipal acceptance | Regional | Map which inspections are already covered under CSA A277 (factory QA, structural, plumbing rough-ins, electrical pre-wiring, firestopping inside modules). List which inspections MUST remain on-site (foundation, hookups, sealing, fire separations, assembly). Review differences in inspection practices across Atlantic municipalities. Draft the shared Framework | Provincial Government | Manufacturers, Developers & General Contractors | 20272027 | Collaboration | - | - | - | - | Pending
15 | Policy and regulatory | Permitting and Approvals | Encourage MMC solutions (e.g., categories 2-4, 6 and 7) that meet Heritage Conservation Act requirements. | Heritage Conservation Act identifies heritage places in unincorporated areas, providing a barrier for housing (NB). | 2026 | PR8 | NB | Provincial Government, Developers & General Contractors, Technical Professionals | Easy | 7 | Reduction in unplanned heritage-related delays Fewer RFIs to the Heritage Branch | Provincial | Confirm which heritage triggers apply in unincorporated areas Summarize permit types (site alteration, impact assessment) Draft short guidance text for Navigation Guide Validate with NB Heritage Branch | Provincial Government | Provincial Government, Developers & General Contractors, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
16 | Policy and regulatory | Permitting and Approvals | Review permitting, by-laws, zoning and pre-construction workflows to remove barriers (e.g., costs, redundant processes, complex approvals, etc.) to all forms of housing supply. This may be done through removal of pre-construction costs, digitizing workflows, educating industry, etc. | Slow and costly approval processes (Atlantic). | 2027 | PR9 | Atlantic | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | Medium | 9 | Average modular permitting time before vs. after track Number of repeatable modular designs pre-verified Increase in modular applications submitted | Local, provincial | Identify which modular designs can be pre-verified. Provide municipalities with CSA certification details. Update municipal workflows to skip factory-completed checks. | Provincial Government, Municipal Government | Developers & General Contractors, Municipal Government, Technical Professionals | 20272027 | Independent | Pending | Pending | Pending | Pending | -
17 | Procurement models and contracts | Competition and Market Dynamics | Collaborate across the four provinces to identify a method to score proponents beyond lowest bid that captures benefits of time savings (speed), environmental, social and cultural KPIs. | Lowest bid procurement often fails to capture the full value and impact of time savings, environmental factors, etc. | 2026 | PM1 | Atlantic | Provincial Government, Academic and Training Institutions, Industry Association | Medium | 8 |  | Provincial, regional |  | Provincial Government | Provincial Government, Academic and Training Institutions, Industry Association | 20262026 | Collaboration | - | - | - | - | Pending
18 | Procurement models and contracts | Competition and Market Dynamics | Create a funding stream (through Opportunities NB, Invest NS, Innovation PEI and NL’s department of IET) for manufacturers to access and become CSA certified. | Only few CSA-certified modular manufacturers, limiting competition, raising costs, and preventing suppliers from scaling confidently (Atlantic). | 2026 | PM2 | Atlantic | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | Easy | 9 | Increase in number of pre-qualified modular suppliers Reduction in average bid prices Number of projects receiving more than 1–2 bids | Regional | Compile list of CSA A277/A660-certified manufacturers in ON/QC Create modular-specific pre-qualification criteria Issue pre-qualification call | Provincial Government | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | 20262026 | Independent | Pending | Pending | Pending | Pending | -
19 | Procurement models and contracts | Competition and Market Dynamics | Use RFIs and/or RFQs to gain information about manufacturers in the region, pre-qualify proponents (there may be an opportunity to leverage the Build Canada Homes data collected through their MMC RFI). (PM3) | Low-bid procurement models do not quantify the benefits of some forms of OSC (cost certainty, shortened schedule, reduction in environmental impact, safer for the skilled workforce) which makes OSC solutions less competitive than stick-built construction (Atlantic). Lack of value-based procurement approaches (Atlantic). | 2026 | PM3 | Atlantic | Developers & General Contractors, Manufacturers, Provincial Government, Federal Government, Municipal Government | Easy | 9 | Number of RFPs using separated cost line items Increase in modular bids submitted Reduction in modular bid disqualification due to upfront costs | Regional | Update procurement templates to require separated cost line items Provide short internal guidance to evaluators | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
20 | Procurement models and contracts | Competition and Market Dynamics | Provinces and non-profit housing providers to publish a rolling 3–4-year forecast of OSC-suitable public housing projects across the region. | Unclear demand and supply conditions create a “chicken-or-egg” problem, limiting competition and complicating procurement planning (Atlantic). | 2026 | PM4 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | Easy | 9 | Number of modular projects included in forecast Manufacturer participation in bids Increase in factory expansion/production planning | Regional | Identify which upcoming public housing projects are modular-compatible Collect capital plans from municipalities + provinces | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
21 | Procurement models and contracts | Competition and Market Dynamics | Use a procurement approach that allows for the manufacturer to be involved in a design assist role during the design phase ( e.g., design-build CCDC-14). | Projects may need to be approved as design-build to create more competition (NS). | 2026 | PM5 | NS | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | Easy | 7 | Increase in number of modular bidders Reduction in redesign hours or change orders | Provincial | Identify modular-suitable projects early Issue RFPs using design–build method | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
22 | Procurement models and contracts | Competition and Market Dynamics | Work with federal and provincial governments to identify serviced or partially serviced small sites and combine them to tender larger projects to one development or design-build team. | Limited land availability reduces how many modular projects can be procured (NS). | 2026 | PM6 | NS | Provincial Government, Manufacturers, Technical Professionals, Municipal Government | Medium | 7 | Number of parcels identified and pre-cleared Number of parcels included in modular tenders Increase in modular-suitable land availability | Provincial | Inventory small provincial & municipal parcels Basic servicing and access assessments Municipal confirmation of allowable uses | Provincial Government | Manufacturers, Municipal Government, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
23 | Procurement models and contracts | Competition and Market Dynamics | Develop a standardized OSC cost library (e.g., RSMeans-aligned) with supply-chain education to improve cost certainty and procurement outcomes | Lack defined roles and responsibilities leading to inaccurate pricing from sub-contractors (PEI) | 2026-2028 | PM7 | PEI | Manufacturers, Developers & General Contractors, Provincial Government | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors | 20282026 | Collaboration | - | - | - | - | Pending
24 | Procurement models and contracts | Design and Standards | Require an OSC or MMC integrator role as part of the project team using the definition identified by NRCan. The integrator may bee a consultant, contractor or manufacturer. | Designs are developed for traditional construction and only adapted to OSC methods later which causes redesign and inefficiencies (Atlantic). | 2026 | PM8 | Atlantic | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | Medium | 9 | Fewer redesign hours Reduction in change orders Number of projects identifying modular feasibility early | Regional | Early design teams receive modular design parameters (grid, module sizes, MEP zones) Consultation with manufacturers during concept design Include modular feasibility as a required step in RFP scopes | Provincial Government, Technical Professionals | Manufacturers, Developers & General Contractors, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
25 | Procurement models and contracts | Design and Standards | Ensure CSA A277 certification and compliance with the building code of the final building location. | Modular builds from other regions may not be designed to meet local performance standards (e.g., hurricane-force winds) (NS, NL). | 2026 | PM9 | NL, NS | Provincial Government, Technical Professionals, Manufacturers, Finance & Insurance/Business Services | Easy | 9 | Reduction in redesign requests post-award Number of proposals with compliant stamped engineering | Provincial | Add requirement for stamped structural verification in all modular RFPs Provide bidders with local wind/snow/climate indices Require early coordination with Atlantic-licensed engineers | Provincial Government | Manufacturers, Technical Professionals, Finance & Insurance/Business Services | 20262026 | Independent | Pending | Pending | Pending | Pending | -
26 | Procurement models and contracts | Design and Standards | Use a procurement approach that enables performance-based on projects where MMC will be used. | Lack of flexible RFP formats - they are too structured and project specific (NB). | 2026 | PM10 | NB | Provincial Government, Manufacturers, Technical Professionals, Developers & General Contractors | Easy | 8 | Number of RFPs using performance-based requirements Increase in modular submissions Reduction in redesign/change-order costs | Provincial | Identify which requirements can be performance-based instead of prescriptive Train evaluators on comparing modular proposals Update RFP templates to include flexible requirements | Provincial Government | Manufacturers, Developers & General Contractors, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
27 | Procurement models and contracts | Manufacturing and Supply Chain | Issue bundled OSC procurement approaches (e.g., offtake agreements) to de-risk capacity investment in the regional manufacturers and add regional logistics supports. | Limited OSC manufacturing capacity and an under-developed supply chain create dependency on imports, transport bottlenecks, and long lead times (Atlantic). | 2026 | PM11 | Atlantic | Manufacturers, Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Finance & Insurance/Business Services, Municipal Government | Medium | 9 | Number of sites included in bundled procurements Factory production allocated to Atlantic projects Reduction in transport delays | Regional |  | Provincial Government | Manufacturers, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers, Finance & Insurance/Business Services | 20262026 | Independent | Pending | Pending | Pending | Pending | -
28 | Procurement models and contracts | Procurement Process | Collaborate with CCDC and across the region to create contract templates for MMC to ensure consistency across the region. | Inconsistent contracting practices for MMC projects (Atlantic). | 2027 | PM12 | Atlantic | Provincial Government, Academic and Training Institutions, Industry Association | Medium | 8 |  | National, regional, provincial |  | Provincial Government, Industry Associations | Provincial Government, Academic and Training Institutions, Industry Association | 20272027 | Collaboration | - | - | - | - | Pending
29 | Procurement models and contracts | Procurement Processes | Encourage tenders to consider MMC categories 1 to 4 alternatives. | Procurement is oriented toward traditional construction reducing acceptance for OSC approaches (Atlantic). | 2026 | PM13 | Atlantic | Provincial Government, Manufacturers, Municipal Government, Developers & General Contractors | Easy | 8 | Number of tenders allowing modular alternatives Number of modular alternative submissions | Regional | Add optional modular submission line to tender documents Provide evaluators guidance on comparing modular vs traditional approaches | Provincial Government, Municipal Government | Manufacturers, Developers & General Contractors, Municipal Government | 20262026 | Independent | Pending | Pending | Pending | Pending | -
30 | Procurement models and contracts | Procurement Processes | After PM3, create consistent RFP processes across the four provinces and provide annual FAQs and training sessions. | New entrants to construction are not used to RFP processes (NB). | 2026 | PM14 | NB | Manufacturers, Developers & General Contractors, Provincial Government | Easy | 7 | Reduction in incomplete modular submissions Increase in number of modular bidders Fewer administrative RFIs | Provincial | Identify common missing/incorrect items in past submissions | Provincial Government | Manufacturers, Developers & General Contractors | 20262026 | Collaboration | - | - | - | - | Pending
31 | Procurement models and contracts | Procurement Processes | Include clear schedule requirements in contracts and link payments to project signing, factory-based project progress, delivery and installation milestones. | Lack of schedule regulations and enforcements (NB, PEI). | 2026 | PM15 | NB, PEI | Provincial Government, Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Easy | 9 | Number of tenders including schedule enforcement Reduction in installation or delivery delays | Provincial, regional | Identify modular-specific scheduling needs Update contract templates to include enforceable schedule milestones | Provincial Government, Municipal Government | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers | 20262026 | Independent | Pending | Pending | Pending | Pending | -
32 | Procurement models and contracts | Procurement Processes | Define OSC-specific responsibilities in trade scopes and use a standardized site-readiness checklist. | Pre-fabrication work is often missing from trade agreements and scopes, making coordination harder (Atlantic). | 2026 | PM16 | Atlantic | Provincial Government, Manufacturers, Developers & General Contractors, Technical Professionals | Medium | 8 | Fewer installation delays due to unclear responsibilities | Regional | Review typical modular scope boundaries (factory vs. on-site) Identify common interface failures on past projects Update procurement templates with modular-specific scope language | Provincial Government | Manufacturers, Developers & General Contractors, Technical Professionals | 20262026 | Independent | Pending | Pending | Pending | Pending | -
33 | Procurement models and contracts | Procurement Processes | Where possible, include detailed site information in RFPs (geotechnical, laydown areas, overhead constraints, site images). | Lack of site access or information for bidders to accurately estimate on-site works (NB). | 2026-2028 | PM17 | NB | Manufacturers, Developers & General Contractors, Provincial Government | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | Provincial Government | Provincial Government, Manufacturers, Developers & General Contractors | 20282026 | Independent | Pending | Pending | Pending | Pending | -
34 | Skilled workforce and skills development | Awareness, Culture & Mindset | Host OSC industry events (tours, seminars) targeting skilled trades. | Workforce resistance to OSC due to lack of familiarity, fear of job loss, or cultural hesitation toward new methods (Atlantic). | 2026 | WD1 | Atlantic | Provincial Government, Industry Associations | Easy | 8 | Attendance at OSC events Surveys on workforce perception of OSC Increased modular adoption | Regional, provincial | Identification of industry professionals to host events Event planning | Provincial Government | Industry Associations | 20262026 | Collaboration | - | - | - | - | Pending
35 | Skilled workforce and skills development | Awareness, Culture & Mindset | Launch OSC awareness campaigns, docuseries, and industry-wide marketing. | Low awareness and misconceptions about OSC quality, aesthetics, and durability (Atlantic). | 2026-2027 | WD2 | Atlantic | Provincial Government, Industry Associations, Manufacturers, Federal Government | Easy | 9 | Public awareness metrics (survey data) Number of facility open houses Participation in outreach | National, regional, provincial | Marketing strategy developed Local case studies collected Cooperation from manufacturers | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | 20272026 | Collaboration | - | - | - | - | Pending
36 | Skilled workforce and skills development | Awareness, Culture & Mindset | Promote OSC careers through coordinated awareness campaigns and industry events. | Limited promotion of modular construction within the industry and workforce (Atlantic). | 2026-2027 | WD3 | Atlantic | Industry Associations, Industry Associations, Manufacturers, Academic/Training Institutions | Easy | 8 | Number of OSC events held Number of sponsorships awarded and recipient career paths Training integration into programs | Regional, provincial, maybe national | Event planning and secured funding for sponsorships | Provincial Government, Manufacturers, Academic/Training Institutions | Manufacturers, Industry Associations, Academic/Training Institutions | 20272026 | Collaboration | - | - | - | - | Pending
37 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Collaborate across Atlantic post-secondary institutions to integrate MMC training and micro-credentials. | NSCC programs closing due to low enrollment (NS). Few contractors have OSC experience, limiting participation (NS). | 2026 | WD4 | NS | Academic/Training Institutions, Provincial Government | Medium | 9 | Enrollment numbers in NSCC modular courses Campaign reach (social media, schools) Number of applications received | Local. provincial | Marketing campaign materials Coordination with NSCC and provincial education authorities | Provincial Government, Academic/Training Institutions | Academic/Training Institutions | 20262026 | Collaboration | - | - | - | - | Pending
38 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Create streamlined credential recognition for internationally trained workers and engage and work with Indigenous communities. | Barriers for foreign-trained workers to gain equivalency; limited culturally appropriate programs for Indigenous communities (NS). | 2026 | WD5 | NS | Industry Associations, Indigenous & Community Organizations, Provincial Government, Academic/Training Institutions | Medium | 8 | Number of foreign-trained workers completing recognition process Number of culturally appropriate programs delivered Participation by Indigenous students | Provincial, regional | Agreements with credentialing bodies Partnerships with Indigenous organizations Development of training content | Provincial Government | Industry Associations, Academic/Training Institutions, Indigenous & Community Organizations | 20262026 | Independent | Pending | Pending | Pending | Pending | -
39 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Collaborate across trade associations to offer heavy equipment and crane operations in workforce outreach. | Limited access to specialized equipment operators (e.g., cranes, certified operators) (Atlantic). | 2026 | WD6 | Atlantic | Industry Associations, Transportation & Logistics Providers, Provincial Government | Difficult | 8 | Counts of shared resources Project delays due to lack of resources | Regional | Coordination agreements between provinces Identification of regional capacity gaps | Provincial Government, Federal Government | Federal Government, Transportation & Logistics Providers, Industry Associations | 20262026 | Collaboration | - | - | - | - | Pending
40 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Work with post-secondary institutions to increase size and staffing in planning and building offices across the region. | Limited capacity and in planning and building offices which can slow project delivery (Atlantic). | 2026 | WD7 | Atlantic | Industry Associations, Manufacturers, Academic/Training Institutions | Medium | 8 |  | Regional, provincial |  | Academic/Training Institutions, Provincial Government | Academic/Training Institutions, Provincial Government | 20262026 | Collaboration | - | - | - | - | Pending
42 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Invest in factory optimization (i.e., digitized processes, automation, etc.) and training to increase capacity and recruitment. | Low overall workforce availability limits the ability to scale modular construction (Atlantic). | 2026-2027 | WD8 | Atlantic | Provincial Government, Industry Associations, Manufacturers, Federal Government | Medium | 9 | Efficiency KPIs folllowing implementation of automation Output per worker Reduced labour bottlenecks | Local, regional | Investment in automation equipment Worker training on new technology | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | 20272026 | Collaboration | - | - | - | - | Pending
43 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Build on the AMC certificate to develop a national curriculum aligned with apprenticeships. | Lack of clear, unified training pathways or standards for OSC across Canada (Atlantic). | 2027 | WD9 | Atlantic | Industry Associations, Academic/Training Institutions | Medium | 8 | Adoption rate of national curriculum by provinces Number of institutions offering courses Enrollment numbers | National, provincial | Align provincial apprenticeship bodies to recognize modular-specific credentials Establish CHBA alignment Approval by national training authorities Funding for curriculum development | FALSE | Industry Associations, Academic/Training Institutions | 20272027 | Collaboration | - | - | - | - | Pending
44 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Expand MMC-focused skilled workforce training, fast-track continuous education opportunities, and industry-supported apprenticeships. | Shortage of skilled trades needed for OSC construction (design, assembly, mass timber, mechanical/electrical, etc.) (NB). | 2027 | WD10 | NB | Provincial Government, Academic/Training Institutions, Industry Associations | Easy | 8 | Number of apprenticeships created Program enrollment Industry placement rates | Regional | College/unions agreement Curriculum development Employer sponsorship secured | Provincial Government, Industry Associations, Academic/Training Institutions | Industry Associations, Academic/Training Institutions | 20272027 | Collaboration | - | - | - | - | Pending
45 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Provide relocation incentives and additional workforce benefits (e.g., housing). | Rural factory locations limit labour access and reduce available workforce pools (Atlantic). | 2027 | WD11 | Atlantic | Provincial Government, Manufacturers, Federal Government | Difficult | 7 | Number of relocation/housing subsidies granted Change in labour availability at rural facilities | Regional, local | Provincial/federal funding approval Policy design for incentives | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government | 20272027 | Collaboration | - | - | - | - | Pending
46 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Identify training for provincial and municipal staff (including engineers, planners, inspectors, architects, project managers, trades, etc.) to educate on leveraging MMC in projects. | Staff shortages in public offices (planning, permitting, fire inspection) delay projects (NB). New building inspectors are inexperienced (NL). | 2027 | WD12 | NB, NL | Municipal Government, Provincial Government, Academic/Training Institutions | Medium | 9 | Number of municipal staff hired Permitting turnaround times Number of inspectors trained Inspector certification rates Reduced inspection delays | Local, provincial | Budget approval Digital permitting system development Curriculum development for inspector training | Provincial Government, Academic/Training Institutions | Provincial Government, Federal Government, Municipal Government | 20272027 | Independent | Pending | Pending | Pending | Pending | -
47 | Skilled workforce and skills development | Skilled Trades & Labour Availability | Collaborate with trade associations to offer training for traditional builders on installation, fit out and handover of category 1 and 2 MMC projects | Skill gaps among builders (Atlantic). | 2027 | WD13 | Atlantic | Industry Associations, Academic/Training Institutions | Easy | 7 |  | Regional, provincial |  | Academic/Training Institutions | Industry Associations, Manufacturers, Academic/Training Institutions | 20272027 | Collaboration | - | - | - | - | Pending
48 | Skilled workforce and skills development | Workforce Retention & Recruitment | Highlight MMC employment benefits and support bursaries, scholarships, mentorships, and DEI training. | Difficulty attracting youth, women, diverse groups, and newcomers to construction trades (Atlantic). | 2026-2027 | WD14 | Atlantic | Municipal Government, Provincial Government, Academic/Training Institutions, Manufacturers, Federal Government, Indigenous & Community Organizations | Medium | 9 | Scholarship uptake Mentorship participation Diversity metrics in workforce | Provincial, regional | Funding approval for scholarships Mentorship program structure | Provincial Government, Indigenous & Community Organizations | Provincial Government, Manufacturers, Federal Government, Municipal Government, Academic/Training Institutions | 20272026 | Collaboration | - | - | - | - | Pending
49 | Skilled workforce and skills development | Workforce Retention & Recruitment | Consult Indigenous communities to identify workforce initiatives. | Culturally inappropriate or unwelcoming workplaces limit participation from Indigenous peoples and underrepresented groups (NB). | 2026-2027 | WD15 | NB | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | Easy | 8 | Number of Indigenous-owned businesses supported DEI training completion Workforce participation rates | Provincial, regional | Funding and program approval DEI curriculum developed | Provincial Government, Indigenous & Community Organizations | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | 20272026 | Independent | Pending | Pending | Pending | Pending | -
50 | Skilled workforce and skills development | Workforce Retention & Recruitment | Enable long-term year-round employment through offtake agreements and enhanced benefits. | Workforce retention challenges due to high living costs, housing affordability, and job security concerns in the construction sector (Atlantic). | 2027 | WD16 | Atlantic | Provincial Government, Manufacturers, Federal Government, Industry Associations | Difficult | 9 | Worker retention rates Housing uptake Employment stability metrics | Local, regional | Policy approval for housing subsidies Government purchasing agreements finalized | Provincial Government, Manufacturers, Federal Government | Provincial Government, Manufacturers, Federal Government, Industry Associations | 20272027 | Collaboration | - | - | - | - | Pending
51 | Transportation and Logistics | Damage and Protection | Ensure conflict resolution for OSC component damages is included in contracts. | Responsibility/liability for damage is unclear between manufacturer, hauler, GC (Atlantic). | 2026 | TL1 | Atlantic | Industry Associations, Developers & General Contractors, Transportation & Logistics Providers, Manufacturers, Finance & Insurance/Business Services | Easy | 7 | Reduction in disputes | Local | Development of formal insurance and liability agreements Stakeholder alignment | Industry Associations, Finance & Insurance/Business Services | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Industry Associations | 20262026 | Independent | Pending | Pending | Pending | Pending | -
52 | Transportation and Logistics | Damage and Protection | Collaborate with the R&D based organizations to better understand and minimize damages from transportation and erection. Produce a document top help mitigate these risks. | Denting, corner damage, and structural movement during loading/unloading (Atlantic). Inconsistent moisture barriers and wrapping practices (Atlantic). | 2027 | TL2 | Atlantic | Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Academic/Training Institutions, Industry Associations | Easy | 8 | Number of training sessions delivered Reports of damage to modules during transportation | National | Transport best-practice guidelines finalized Training content developed | Academic/Training Institutions | Manufacturers, Developers & General Contractors, Transportation & Logistics Providers, Industry Associations, Academic/Training Institutions | 20272027 | Collaboration | - | - | - | - | Pending
53 | Transportation and Logistics | Module size and road restrictions | Collaborate regionally to document overload escort and permit requirements in a single reference. | Escort and permit rules for oversized modules (often >12 ft wide) differ between jurisdictions (Atlantic). | 2026 | TL3 | Atlantic | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | Medium | 9 | Number of agreements signed Reduced delays due to permit harmonization Number of municipalities participating | Local, provincial, regional | Regulatory coordination between provinces Legal framework for transport agreements | Provincial Government, Municipal Government | Provincial Government, Developers & General Contractors, Municipal Government, Transportation & Logistics Providers | 20262026 | Collaboration | - | - | - | - | Pending
54 | Transportation and Logistics | Module size and road restrictions | Using resources created from TL5, consider developing design guidelines that account for manufacturing, transportation, and assembly by province based on transportation and logistics constraints. | Module width/height is constrained by bridge clearances, turning radii, and road widths (Atlantic). Modules must be designed to match available island transport equipment (NL). | 2027 | TL4 | Atlantic, NL | Provincial Government, Technical Professionals, Manufacturers | Medium | 7 | Data collected on road restrictions Number of transportation-friendly designs used | Provincial, local | Data collection on bridges, roads, turning radii Mapping infrastructure conflicts Design catalogue development Coordination between designers, manufacturers, transport providers | Provincial Government, Manufacturers | Provincial Government, Technical Professionals, Manufacturers | 20272027 | Independent | Pending | Pending | Pending | Pending | -
55 | Transportation and Logistics | Module size and road restrictions | Develop a regional logistics framework and database map for oversized loads in collaboration with provincial and municipal transportation authorities, ferry operators, energy authorities and other groups who maintain infrastructure in the right-of-way. (TL5) | Ferry costs add major expense for panelized construction (NL). | 2027 | TL5 | NL | Provincial Government, Transportation & Logistics Providers | Easy | 8 | Number of ferry trips using discounted/off-peak rates Cost savings On-time deliveries | Provincial | Agreements with ferry operators Approval of subsidy program | Provincial Government, Transportation & Logistics Providers | Provincial Government, Transportation & Logistics Providers | 20272027 | Collaboration | - | - | - | - | Pending
56 | Transportation and Logistics | Site access and Storage constraints | In parallel to TL5, identify designated transportation routes with temporary staging yards for critical projects. | Limited staging and storage space near construction sites (Atlantic). Seasonal weight restrictions affecting transportation timelines (Atlantic). Difficult access in dense urban areas (tight roads, overhead utilities) (NS). | 2026 | TL6 | Atlantic, NS | Provincial Government, Academic/Training Institutions, Industry Associations | Difficult | 8 | Number of staging yards designated Reduction in delivery delays Improvement in on-time module deliveries | Local, provincial | Database of land potentiall available for staging near sites | Provincial Government | Provincial Government, Municipal Government, Transportation & Logistics Providers | 20262026 | Independent | Pending | Pending | Pending | Pending | -