## Sheet1
ID | Category | Sub-Category | Location Identified | Owner(s) | Contributor(s) | Filtering-Contributors-Categories | Expected Timeline | Ease of Implementation | Impact (out of 10) | Metrics | Scope of Implementation | Preqrequisite initiative (s) | Sorting helper col 1 | Sorting Helper col 2 | Updated Barrier Description | Initiative | NB Status | NS Status | PEI Status | NL Status | Regional | Metric Notes
FI1 | Financing and Insurance | Access to Financing | Atlantic Region | Provincial Departments of Finance Atlantic Credit Union Associations | Major banks (RBC, TD, Scotiabank, CIBC, BMO), regional credit unions, developers & modular manufacturers, CMHC (reference alignment) | Provincial Government, Finance & Insurance/Business Services, Federal Government | 2026 | Easy | 8 | Number of lenders adopting the brief Reduction in financing rejections for modular Increase in modular mortgage approvals | Regional | Gather modular timeline + risk data from manufacturers | FI | 1 | Banks and lenders do not fully understand or accept modular/off-site construction because of high perceived risks in OSC. | Create an OSC lending brief to improve lender understanding and financing options. | - | - | - | - | In progress | This is a sample metric note.
FI2 | Financing and Insurance | Access to Financing | Atlantic Region | Provincial Departments of Finance Atlantic Credit Union Associations | First-time buyers, credit unions (large role), mortgage brokers, modular manufacturers, community development agencies | Provincial Government, Finance & Insurance/Business Services, Manufacturers | 2026 | Easy | 8 | Increase in number approved modular mortgages under 2 units | Regional | Gather current data on mortgage options. | FI | 2 | Limited financing options for small-scale ownership (e.g., single units, duplexes) force many buyers to rely on high-interest lenders. | Create and use the lending brief to expand mortgage options. | - | - | - | - | Complete/ In action
FI3 | Financing and Insurance | Access to Financing | Atlantic Region | Provincial Departments of Finance | Major banks (RBC, TD, Scotiabank, CIBC, BMO), regional credit unions, developers & modular manufacturers, CMHC (reference alignment) | Provincial Government, Finance & Insurance/Business Services, Federal Government | 2026 | Easy | 9 | Reduction in modular project financing delays | Regional | Build a sample modular draw schedule Document cash-flow needs for modular builds | FI | 3 | Financing rules, mortgage products, and banking policies are outdated for OSC. | Modernize lender policies by educating and clarifying OSC payment and draw schedules. | - | - | - | - | Pending
FI4 | Financing and Insurance | Access to Financing | NS | Nova Scotia Department of Finance | NS credit unions, local lenders & community investment funds, developers, modular manufacturers | Provincial Government, Finance & Insurance/Business Services, Manufacturers | 2026 | Easy | 7 | Reduced reliance on one or two banks Increase in competitive interest rates for modular | Provincial | Prepare NS-specific version of the brief | FI | 4 | Lack of competition among funding providers. | Create and share a lending brief with private investors (banks, large REIT) and institutional investors in the region and outside Atlantic Canada. | Pending | Pending | Pending | Pending | -
FI5 | Financing and Insurance | Cost Structure | Atlantic Region | Provincial Departments of Finance Credit Union Associations | Manufacturers, developers, lenders, CMHC, Construction managers | Provincial Government, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | 2026 | Easy | 9 | Number of lenders adopting modular-friendly draw schedules Reduced delays caused by payment timing | Regional | Document typical modular cost curves Build standard modular draw templates | FI | 5 | High upfront costs and misaligned payment milestones strain cash flow. | Add OSC-friendly payment frameworks and liquidity supports. | - | - | - | - | Pending
FI6 | Financing and Insurance | Cost Structure | Atlantic Region | Provincial Departments of Finance | Modular manufacturers (input providers), Developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders (for underwriting consistency) | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | FI | 6 | Challenges producing accurate pricing estimates due to immature market. | Educate the supply chain and develop an OSC cost library with standardized cost ranges (e.g., RS Means). | - | - | - | - | Pending
FI7 | Financing and Insurance | Cost Structure | PEI | PEI Housing Corporation PEI Department of Transportation & Infrastructure PEI Procurement | PEI modular developers, general contractors, non-profits and community housing providers, transport companies & crane operators, ferry operators (Marine Atlantic if applicable for interprovincial shipments), modular manufacturers supplying to PEI | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services, Transportation & Logistics Providers | 2027 | Medium | 9 | Reduction in module transport cost Number of projects participating in shared logistics Increased adoption of modular for multi-unit builds | Provincial | Establish a framework for comparing OSC approaches for PEI conditions | FI | 7 | Multi-unit residential building (MURB) volumetric modular construction significantly more expensive. | Use existing MURB VMC projects as a case study to identify cost reductions or work with all forms of OSC to determine the best approach to buildings MURBs on PEI. | Pending | Pending | Pending | Pending | -
FI8 | Financing and Insurance | Cost Structure | NS,NB | Provincial Housing Agencies (NSPHA, NB Housing) Provincial Procurement Divisions | Small modular manufacturers, developers, general contractors, insurers, lenders | Manufacturers, Provincial Government, Finance & Insurance/Business Services | 2026 | Medium | 8 | Number of modular tenders allowing pre-qualified suppliers without full bonding Increase in bid participation Reduced project cancellations due to lack of bonded bidders | Provincial | Define modular-specific qualification criteria Review manufacturer QA, capacity, and safety documentation | FI | 8 | Bonding challenges for small manufacturers | Introduce a OSC supplier pre-qualification pathway based on the factory’s CSA certification. | Pending | Pending | Pending | Pending | -
FI9 | Financing and Insurance | CMHC Misalignment | Atlantic Region | CMHC Regional Office Atlantic Provincial Housing Agencies | Modular manufacturers, developers, lenders, municipal planners, project managers | Federal Government, Developers & General Contractors, Finance & Insurance/Business Services, Technical Professionals, Provincial Government | 2026 | Medium | 9 | Reduced CMHC approval time for modular files Increase in successful modular applications | Regional | Collect standard modular factory timelines from local manufacturers Compare with CMHC approval timelines Identify specific misalignment points Draft modular timeline recommendations | FI | 9 | CMHC policies do not align with OSC timelines, delivery methods, or cost structure. | Establish a CMHC–regional coordination group. | - | - | - | - | Pending
FI10 | Financing and Insurance | CMHC Misalignment | Atlantic Region | CMHC Atlantic Provincial Housing Agencies Municipal planning | Developers, modular manufacturers, project teams | Developers & General Contractors, Manufacturers, Provincial Government, Federal Government, Municipal Government | 2026 | Easy | 7 | Fewer CMHC refusals due to non-residential shares | Regional | Gather PEI/NS/NB/NL examples of mixed-use zoning conditions Identify CMHC concerns about non-residential % Provide modular project examples to CMHC for comparison | FI | 10 | Restrictions on funding non-residential space in new buildings. | Develop consistent criteria for reviewing mixed-use OSC buildings. | - | - | - | - | Pending
FI11 | Financing and Insurance | CMHC Misalignment | Atlantic Region | CMHC Regional Office Atlantic Provincial Housing Agencies | Developers, modular manufacturers, municipalities, lenders | Provincial Government, Federal Government, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | Easy | 8 | Reduction in incomplete CMHC submissions Higher approval rates for modular files | Regional | Consolidate CMHC documentation requirements Summarize modular-specific questions asked by CMHC | FI | 11 | Lack of clarity on how to access CMHC programs and funding streams. | Work with CMHC to create a simplified guide targeted to the needs of Atlantic Canada. | - | - | - | - | Pending
FI12 | Financing and Insurance | CMHC Misalignment | Atlantic Region | Provincial Housing Departments CMHC | Municipalities, regional planning commissions, developers | Federal Government, Developers & General Contractors, Technical Professionals | 2026 | Medium | 9 | More rural modular projects approved | Regional | Gather updated rural housing data Compare with CMHC’s national dataset Provide corrected figures | FI | 12 | CMHC data for rural areas is outdated/incorrect. | Identify and share updated rural housing data with CMHC. | - | - | - | - | Pending
FI13 | Financing and Insurance | Insurance | Atlantic Region | Insurance brokers specializing in construction Warranty providers Developers Modular manufacturers | Manufacturers, transporters, crane companies, general contractors, warranty providers, lenders, CMHC | Manufacturers, Transportation & Logistics Providers, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | 2026 | Medium | 9 | Number of modular projects using wrap-up all-risk coverage Reduction in duplicated premiums Fewer liability disputes Warranty acceptance rate for modular modules Lower overall insurance cost per unit | Regional | Manufacturers + developers jointly approach insurance brokers Brokers prepare integrated wrap-up policy options Legal teams insert handover protocol clauses into modular contracts | FI | 13 | There are coverage gaps, overlapping insurance requirements, and unclear responsibility transfers between the factory, transporter, and on-site contractor. | Work with the insurance sector to develop a unified OSC insurance model with clear liability transfer. | - | - | - | - | Pending
FI14 | Financing and Insurance | Insurance | Atlantic Region | Insurance brokers Major insurers operating in Atlantic Canada Modular manufacturers | Manufacturers, developers, lenders, warranty providers, provincial housing agencies. | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services, Provincial Government | 2026 | Medium | 8 | Reduction in builder’s-risk premiums for mass-timber modular Number of factories certified with risk-reduction controls Number of projects qualifying for the credit | Regional | Identify typical OSC roles and responsibilities from the start to completion of projects. | FI | 14 | Higher insurance premiums for mass timber or wood-based modular systems. | Work with the insurance sector to develop a unified OSC insurance model with clear liability transfer. | - | - | - | - | Pending
FI15 | Financing and Insurance | Insurance | Atlantic Region | Insurance Bureau of Canada Commercial insurers Insurance brokers | Manufacturers, developers, lenders, warranty providers, provincial housing agencies. | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services | 2026 | Medium | 9 | Reduction in premiums for modular factories Number of factories moved to the new risk category | Regional | Identify typical OSC roles and responsibilities from the start to completion of projects. | FI | 15 | Insurance regulations not tailored to offsite fabrication risks. | Work with the insurance sector to develop a unified OSC insurance model with clear liability transfer. | - | - | - | - | Pending
FI16 | Financing and Insurance | Incentives & Policy | Atlantic Region | Nova Scotia Provincial Housing Agency New Brunswick Housing Corporation PEI Housing Corporation NL Housing Corporation Provincial Departments of Finance | Modular manufacturers, developers, non-profits, lenders, municipal housing partners, CMHC | Manufacturers, Provincial Government, Federal Government, Indigenous & Community Organizations, Developers & General Contractors | 2027 | Medium | 8 | Number of modular units delivered under the credit Reduction in per-unit cost for provincial housing builds Increase in manufacturer production volume | Provincial, regional | Determine per-unit credit value (e.g., $2,000–$5,000/unit) Set eligibility (affordable housing, supportive housing, repeatable modular designs) Secure small annual budget allocation Develop simple claim process at delivery or installation | FI | 16 | No tax incentives, subsidies, or financial supports tailored to OSC. | Develop and use a pre-manufactured index to encourage the use of OSC or other forms of MMC and increase productivity. | Pending | Pending | Pending | Pending | Pending
FI17 | Financing and Insurance | Incentives & Policy | Atlantic Region | Municipal Planning & Permitting Departments Provincial Housing Agencies (NSPHA NB Housing PEI Housing NL Housing) Provincial Departments of Municipal Affairs | Developers, manufacturers, municipal building officials, lenders. | Municipal Government, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | Medium | 7 | Number of modular projects qualifying for adjusted fees Reduction in average fees paid per modular project Decrease in municipal review time per project Increase in modular applications submitted | Provincial, regional | Define what qualifies as “repeatable modular design” Establish pre-verified plan sets or modular typologies Update municipal fee schedules to include modular track | FI | 17 | Government fees add affordability challenges. | Offer reduced fees for pre-verified OSC designs. | Pending | Pending | Pending | Pending | Pending
PM1 | Procurement Models and Contracts | Competition and Market Dynamics | Atlantic Region | NSPHA NB Housing PEI Housing NL Housing Provincial Procurement Divisions | Local modular manufacturers, out-of-region CSA-certified firms, developers, general contractors, lenders. | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | Easy | 9 | Increase in number of pre-qualified modular suppliers Reduction in average bid prices Number of projects receiving more than 1–2 bids | Regional | Create modular-specific pre-qualification criteria Issue pre-qualification call | PM | 1 | Only few CSA-certified modular manufacturers, limiting competition, raising costs, and preventing suppliers from scaling confidently. | Create a funding stream (through Opportunities NB, Invest NS, Innovation PEI and NL’s department of IET) for manufacturers to access and become CSA certified. | - | - | - | - | Pending
PM2 | Procurement Models and Contracts | Competition and Market Dynamics | Atlantic Region | NSPHA NB Housing PEI Housing NL Housing Provincial Procurement Divisions | Developers, modular manufacturers, general contractors, cost consultants, municipal housing partners | Developers & General Contractors, Manufacturers, Provincial Government, Municipal Government | 2026 | Easy | 9 | Number of RFPs using separated cost line items Increase in modular bids submitted Reduction in modular bid disqualification due to upfront costs | Regional | Update procurement templates to require separated cost line items Provide short internal guidance to evaluators | PM | 2 | Low-bid procurement models do not quantify the benefits of some forms of OSC (cost certainty, shortened schedule, reduction in environmental impact, safer for the skilled workforce) which makes OSC solutions less competitive than stick-built construction. | Use RFIs and RFQs to pre-qualify proponents, scoring them on KPIs beyond lowest bid. Include environment, social and culture KPIs in the proponent assessment process of an RFP. | - | - | - | - | Pending
PM3 | Procurement Models and Contracts | Competition and Market Dynamics | Atlantic Region | Provincial Housing Agencies (NSPHA, NB Housing, PEI Housing, NLHC) Provincial Procurement Divisions Departments of Municipal Affairs & Housing | Modular manufacturers, developers, lenders, general contractors, municipalities. | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | 2026 | Easy | 9 | Number of modular projects included in forecast Manufacturer participation in bids Increase in factory expansion/production planning | Regional | Identify which upcoming public housing projects are modular-compatible Collect capital plans from municipalities + provinces | PM | 3 | Unclear demand and supply conditions create a “chicken-or-egg” problem, limiting competition and complicating procurement planning. | Publish a rolling 3-4-year forecast of OSC-suitable (VMC or category 1 and panelized or category 2) public housing projects. | - | - | - | - | Pending
PM4 | Procurement Models and Contracts | Competition and Market Dynamics | NS | Nova Scotia Provincial Housing Agency Nova Scotia Procurement (Service Nova Scotia) | Modular manufacturers, planners, developers, municipalities, provincial land agencies | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | 2026 | Easy | 7 | Increase in number of modular bidders Reduction in redesign hours or change orders | Provincial | Identify modular-suitable projects early Issue RFPs using design–build method | PM | 4 | Projects may need to be approved as design-build to create more competition. | Use design–build procurement on projects that warrant a DB approach (e.g., >8 units). | Pending | Pending | Pending | Pending | -
PM5 | Procurement Models and Contracts | Competition and Market Dynamics | NS | Nova Scotia Provincial Housing Agency Municipalities Department of Public Works / Municipal Affairs | Modular manufacturers, design–build contractors, architects, engineers, developers, municipalities. | Provincial Government, Manufacturers, Technical Professionals, Municipal Government | 2026 | Medium | 7 | Number of parcels identified and pre-cleared Number of parcels included in modular tenders Increase in modular-suitable land availability | Provincial | Inventory small provincial & municipal parcels Basic servicing and access assessments Municipal confirmation of allowable uses | PM | 5 | Limited land availability reduces how many modular projects can be procured. | Work with federal and provincial government to identify serviced or partially serviced small sites and combine to tender larger projects for one DB team. | Pending | Pending | Pending | Pending | -
PM6 | Procurement Models and Contracts | Competition and Market Dynamics | PEI | Provincial Departments of Finance | Modular manufacturers, developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders | Manufacturers, Developers & General Contractors, Provincial Government | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work. | PM | 6 | Lack defined roles and responsibilities leading to inaccurate pricing from sub-contractors. | Develop a modular cost library with standardized cost ranges and typical modular inputs. | - | - | - | - | Pending
PM7 | Procurement Models and Contracts | Design and Standards | Atlantic Region | Provincial Housing Agencies Municipal Housing Units Architectural teams Provincial Procurement Divisions | Architects, engineers, modular manufacturers, developers, general contractors. | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | 2026 | Medium | 9 | Fewer redesign hours Reduction in change orders Number of projects identifying modular feasibility early | Regional | Early design teams receive modular design parameters (grid, module sizes, MEP zones) Consultation with manufacturers during concept design Include modular feasibility as a required step in RFP scopes | PM | 7 | Designs are developed for traditional construction and only adapted to OSC methods later which causes redesign and inefficiencies. | Include an OSC integrator in the project team which supports the OSC feasibility assessment completed during the design phase. | - | - | - | - | Pending
PM8 | Procurement Models and Contracts | Design and Standards | Atlantic Region | Provincial Housing Agencies Municipal Housing Units Architectural teams Provincial Procurement Divisions | Architects, engineers, modular manufacturers, developers, general contractors. | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | 2026 | Medium | 9 | Number of RFPs using performance-based criteria Reduction in redesign hours Fewer modular bids rejected due to prescriptive design conflicts Increase in modular participation in tenders | Regional | Update design scopes to remove prescriptive structural and layout requirements Provide architects a set of modular design parameters (module sizes, grid, spans) Include modular considerations during concept/schematic design stages | PM | 8 | Lack of OSC-friendly designs and prescriptive requirements cause redesign, inefficiencies, and excludes OSC methods. | Enable performance-based criteria. | - | - | - | - | Pending
PM9 | Procurement Models and Contracts | Design and Standards | NS, NL | Provincial Housing Agencies Municipal Building/Permitting Departments Provincial Procurement Divisions | Structural engineers, modular manufacturers, permitting officials, developers, insurers. | Provincial Government, Technical Professionals, Manufacturers, Finance & Insurance/Business Services | 2026 | Easy | 9 | Reduction in redesign requests post-award Number of proposals with compliant stamped engineering | Provincial | Add requirement for stamped structural verification in all modular RFPs Provide bidders with local wind/snow/climate indices Require early coordination with Atlantic-licensed engineers | PM | 9 | Modular builds from other regions may not be designed to meet local performance standards (e.g., hurricane-force winds). | Ensure CSA A277 certification and emphasize the importance of the builds needing to meet building code of final building location. | Pending | Pending | Pending | Pending | -
PM10 | Procurement Models and Contracts | Procurement Processes | Atlantic Region | Provincial Procurement Divisions Provincial Housing Agencies Municipal Procurement Offices | Modular manufacturers, contractors, designers, cost consultants, municipal and provincial evaluators. | Provincial Government, Manufacturers, Municipal Government, Developers & General Contractors | 2026 | Easy | 8 | Number of tenders allowing modular alternatives Number of modular alternative submissions | Regional | Add optional modular submission line to tender documents Provide evaluators guidance on comparing modular vs traditional approaches | PM | 10 | Procurement is oriented toward traditional construction reducing acceptance for OSC approaches. | Encourage tenders to use OSC alternatives. | - | - | - | - | Pending
PM11 | Procurement Models and Contracts | Procurement Processes | Atlantic Region | Provincial Procurement Divisions Provincial Housing Agencies Municipal Procurement Offices | Evaluators, modular manufacturers, contractors, architects, engineers, cost consultants. | Provincial Government, Manufacturers, Developers & General Contractors | 2026 | Medium | 9 | % of tenders with value-based scoring Increase in modular bids that reach evaluation stage Reduction in disqualification of modular proposals due to cost-only scoring | Regional | Identify value-based criteria relevant to modular (schedule, QA, site disruption) Update tender evaluation templates Train procurement staff on new evaluation weighting | PM | 11 | Lack of value-based procurement approaches. | Use RFIs and RFQs to pre-qualify proponents, scoring them on KPIs beyond lowest bid. Include environment, social and culture KPIs in the proponent assessment process of an RFP. | - | - | - | - | Pending
PM12 | Procurement Models and Contracts | Procurement Processes | NB | NB Housing | Modular manufacturers (especially small/new ones), general contractors, procurement evaluators. | Manufacturers, Developers & General Contractors, Provincial Government | 2026 | Easy | 7 | Reduction in incomplete modular submissions Increase in number of modular bidders Fewer administrative RFIs | Provincial | Identify common missing/incorrect items in past submissions | PM | 12 | New entrants to construction are not used to RFP processes. | Create consistent RFP processes across the four provinces and provide an FAQ and training session annually. | Pending | Pending | Pending | Pending | -
PM13 | Procurement Models and Contracts | Procurement Processes | NB | Provincial Departments of Finance | Modular manufacturers, developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders | Manufacturers, Developers & General Contractors, Provincial Government | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Create a standardized checklist of details to include in RFPs. | PM | 13 | Lack of site access or information for bidders to accurately estimate on-site works. | Include as much detail in the RFPs as possible (e.g., geotechnical report, potential laydown areas, potential overhead constraints, etc.) as well as images of the site to ensure proponents provide an accurate estimate. | - | - | - | - | Pending
PM14 | Procurement Models and Contracts | Procurement Processes | NB, PEI | NB Strategic Procurement PEI Procurement Provincial Housing Agencies Municipal Project Managers | Modular manufacturers, site contractors, crane companies, tansport companies, developers, project managers. | Provincial Government, Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026 | Easy | 9 | Number of tenders including schedule enforcement Reduction in installation or delivery delays | Provincial, regional | Identify modular-specific scheduling needs Update contract templates to include enforceable schedule milestones | PM | 14 | Lack of schedule regulations and enforcements. | Include clear schedule requirements in contracts and link payments to project signing, factory-based project progress, delivery and installation milestones. | Pending | Pending | Pending | Pending | Pending
PM15 | Procurement Models and Contracts | Procurement Processes | NB | NB Strategic Procurement NB Housing | Modular manufacturers, architects, engineers, general contractors, developers. | Provincial Government, Manufacturers, Technical Professionals, Developers & General Contractors | 2026 | Easy | 8 | Number of RFPs using performance-based requirements Increase in modular submissions Reduction in redesign/change-order costs | Provincial | Identify which requirements can be performance-based instead of prescriptive Train evaluators on comparing modular proposals Update RFP templates to include flexible requirements | PM | 15 | Lack of flexible RFP formats - they are too structured and project specific. | Use flexible, performance-based RFPs. | Pending | Pending | Pending | Pending | -
PM16 | Procurement Models and Contracts | Procurement Processes | Atlantic Region | Provincial Procurement Divisions Provincial Housing Agencies | Modular manufacturers, subtrades (electrical, plumbing, HVAC, finishes), general contractors, inspectors, engineers, quantity surveyors. | Provincial Government, Manufacturers, Developers & General Contractors, Technical Professionals | 2026 | Medium | 8 | Fewer installation delays due to unclear responsibilities | Regional | Review typical modular scope boundaries (factory vs. on-site) Identify common interface failures on past projects Update procurement templates with modular-specific scope language | PM | 16 | Pre-fabrication work is often missing from trade agreements and scopes, making coordination harder. | Define OSC-specific responsibilities in trade scopes and use a standardized site-readiness checklist. | - | - | - | - | Pending
PM17 | Procurement Models and Contracts | Manufacturing and Supply Chain | Atlantic Region | Provincial Housing Agencies (NSPHA, NB Housing, PEIHC, NLHC) Provincial Procurement Divisions | Modular manufacturers, transport companies, crane operators, site contractors, developers, lenders, municipal partners. | Manufacturers, Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Finance & Insurance/Business Services, Municipal Government | 2026 | Medium | 9 | Number of sites included in bundled procurements Factory production allocated to Atlantic projects Reduction in transport delays | Regional | Identify regional OSC manufacturers and assess production capacity. Analyze demand forecasts to determine bundling opportunities | PM | 17 | Limited OSC manufacturing capacity and an under-developed supply chain create dependency on imports, transport bottlenecks, and long lead times. | Issue bundled OSC procurement approaches (e.g., offtake agreements) to de-risk capacity investment in the regional manufacturers and add regional logistics supports. | - | - | - | - | Pending
PM18 | Procurement Models and Contracts | Manufacturing and Supply Chain | NB | NB Housing NB Power Utility Providers (gas, water) | Modular manufacturers, site contractors, utility companies, crane/transport teams, developers, municipal inspectors. | Manufacturers, Developers & General Contractors, Provincial Government, Municipal Government, Transportation & Logistics Providers | 2026 | Medium | 8 | Number of tenders with confirmed servicing dates Reduction in installation delays caused by utilities | Provincial | Early coordination meeting with utility providers Confirm servicing capacity and timelines. Identify qualified professionals to be an OSC integrator. | PM | 18 | The timing for servicing and installing utilities like water, power and gas is uncertain. | Involve an OSC integrator or mature GC/CM to coordinate OSC project timelines efficiently with utility suppliers. | Pending | Pending | Pending | Pending | -
PR1 | Policy and Regulatory | Attitudes and Knowledge Gaps | Atlantic Region | Provincial Housing Departments Municipal Affairs | Municipal planning departments building officials, manufacturers, CMHC regional staff | Municipal Government, Provincial Government, Federal Government, Manufacturers | 2027 | Medium | 9 | Number of projects approved Approval time Number of departments using pathway | Regional | Development of clear eligibility criteria for selecting modular demonstration projects. Creation of a standardized modular submission package for applicants. Preparation of a modular review checklist for inspectors and permitting staff. | PR | 1 | There is a gap between the promotion of OSC and the acceptance of it. Specifically, politicians have been promoting OSC however their departments do not prefer it. A gap was also noted in CMHC promoting OSC despite the funding mechanisms not being friendly to OSC. | Support the public and private sector in education and create a regional OSC approval pathway supported by coordinated public-awareness program. | - | - | - | - | Pending
PR2 | Policy and Regulatory | Attitudes and Knowledge Gaps | NB | NB Department of Local Government and Local Governance Reform (DLGLR) | Municipal planning departments, development officers, NB Housing, CMHC regional office, NB Building Officials Association, developers & modular manufacturers | Municipal Government, Provincial Government, Federal Government, Manufacturers, Developers & General Contractors | 2026 | Easy | 7 | Number of municipalities adopting the terminology Reduction in terminology-related rejections Consistency in NB Housing program applications | Local, provincial | Drafting of a concise modular terminology list based on CSA standards. Internal review by NB Housing, DLGLR, and municipal planners to confirm usability. Development of a short implementation memo instructing municipalities to adopt the terminology. | PR | 2 | Lack of alignment in terminology from funders. Ambiguity in terminology leading to confusion. | Adopt the MMC Definition Framework across provincial and municipal policies, procurement documents and contracts. | Pending | Pending | Pending | Pending | -
PR3 | Policy and Regulatory | Attitudes and Knowledge Gaps | NB | NB Office of the Chief Medical Officer of Health (Public Health) NB Department of Local Government & Local Governance Reform (DLGLR) | Regional Planning Commission, development officers, NB Housing, municipal councils, public health officers | Municipal Government, Provincial Government | 2026 | Easy | 6 | Number of planning decisions referencing the Note. | Provincial | Drafting of the Healthy Housing Planning Note by NB Public Health with input from planning staff. Review and approval by DLGLR for integration into municipal planning processes. Distribution and short briefing session for development officers and planning commissions. | PR | 3 | Lack of emphasis of the impact of housing on population health | Develop an NB Healthy Housing Planning Note linking housing and year-round safe employment to population health. | Pending | Pending | Pending | Pending | -
PR4 | Policy and Regulatory | Codes and Standards | Atlantic Region | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Building officials, municipal plan reviewers, housing departments, modular manufacturers, consulting engineers | Provincial Government, Technical Professionals, Manufacturers | 2027 | Medium | 8 | Change in average permit review times for modular projects (before vs after guide) Number of municipalities that formally adopt or reference the AM-CNG in procedures Number of RFIs or code-related clarifications requested on modular submissions (aim: decrease) Number of building officials / plan reviewers trained using the guide | Regional | Inventory of existing modular-related code interpretations and issues Draft modular-specific code navigation guide for review Pilot the updates and educational sessions with a small set of municipalities / projects. | PR | 4 | Complexity of codes: mention of challenges navigating national, provincial, and local codes (including NBC, NECB). | At a regional level, work with the NRC to create a technical committee to update the code for OSC and educate planners, architects, building officials and relevant industry members. | - | - | - | - | Pending
PR5 | Policy and Regulatory | Codes and Standards | NS | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Building officials, municipal plan reviewers, housing departments, modular manufacturers, consulting engineers, architects | Provincial Government, Technical Professionals, Manufacturers | 2027 | Medium | 8 | Number of municipalities that formally adopt it Reduction in modular projects flagged for seismic/accessibility differences Reduction in RFIs for out-of-province modular submissions Approval timelines (before vs after) | Regional | Identify common conflicts to adopting CSA A277. Regional meeting with code officials to agree on acceptable approaches. | PR | 5 | Challenges related to codes and standards differing between provinces and municipalities. In addition to accessibility codes and seismic requirements differing across the country. | Encourage adoption of CSA A277 across the province and all municipalities regardless of location of OSC factories (as they need to build to the code of final modular destination). | - | - | - | - | Pending
PR6 | Policy and Regulatory | Government Coordination | Atlantic Region | Department of Public Safety (NB) NB Housing Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) Newfoundland and Labrador Housing Corporation (NLHC) | Provincial Building Code / Technical Standards branches, Municipal Affairs / Municipal Planning divisions, provincial procurement units, municipal planning commissions Atlantic Building Officials Association, modular manufacturers, key federal partners (CMHC Atlantic) | Provincial Government, Municipal Government, Manufacturers, Federal Government | 2026 | Easy | 8 | Number of coordination meetings held Number of cross-department issues resolved Feedback from departments on clarity of roles | Regional | Identify representatives from Housing, Planning, Code, and Procurement in each province. Agree on basic Terms of Reference (purpose: modular-related coordination only). Create a shared information template for departments to submit updates/issues. Schedule quarterly virtual meetings (Atlantic-wide). | PR | 6 | Lack of communication across government agencies. | Establish the Atlantic Off-site Housing Innovation Network with a clear mandate including monthly (or quarterly inter-provincial meetings) with up to two points-of-contact reporting back to provincial committees. | - | - | - | - | Pending
PR7 | Policy and Regulatory | Government Coordination | NL | Service NL - Built Environment Division NL Housing Corporation | Municipal building officials, municipal planning departments, provincial procurement division, NL Housing project managers, modular manufacturers delivering to NL, Office of the Fire Commissioner | Provincial Government, Technical Professionals, Municipal Government | 2026 | Easy | 7 | Number of modular projects supported by the liaison Reduction in RFI volume related to outdated policies Faster issue resolution times (before vs after designation) Reduction in approval delays | Provincial | Assign an existing staff member in Service NL as Modular Liaison Officer (no new hiring needed). Establish mandate: resolve outdated-policy conflicts, coordinate with NL Housing, guide modular projects. Set up an intake channel like email or form for modular-related questions. Hold initial coordination meetings with NL Housing and priority municipalities. Start tracking outdated policies to inform future modernization efforts. | PR | 7 | Outdated policies needing to be updated. | Designate a VMC Liaison Officer in NL. | Pending | Pending | Pending | Pending | -
PR8 | Policy and Regulatory | Inspections | NS | NS Department of Municipal Affairs & Housing – Building and Technical Standards Division Office of the Fire Marshal Nova Scotia Provincial Housing Agency | NS Building Officials Association, municipal building officials & development officers, modular manufacturers shipping into NS, general contractors & installation crews, electrical and plumbing inspectors (as needed), NSPHA project managers | Provincial Government, Technical Professionals | 2026 | Medium | 8 | Reduction in coordination issues reported. Reduction in duplicated site activities or installation delays Faster turnaround for modular installation scheduling Number of municipalities using it. Feedback from contractors and building officials on clarity | Provincial | Identify the roles and responsibilites of all involved in a project early in the project timeline. Identify qualified professionals to be an OSC integrator and support the training of experienced GCs to develop OSC integration skills. | PR | 8 | Operational complexity with OSC due to multiple contractors and on-site and off-site teams. | Involve an OSC integrator or mature GC/CM in projects >8 units to support on- and off-site coordination. | Pending | Pending | Pending | Pending | -
PR9 | Policy and Regulatory | Inspections | Atlantic Region | Nova Scotia Building Officials Association New Brunswick Building Officials Association Municipal Building Officials Association of Prince Edward Island Newfoundland and Labrador Building Officials Association Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Municipal building officials across Atlantic Canada, modular manufacturers (CSA A277 certified), installation contractors, NSPHA, NB Housing, PEI Housing, NL Housing, Office of the Fire Marshal (provincial), developers using modular systems | Provincial Government, Manufacturers, Developers & General Contractors | 2027 | Medium | 9 | Reduction in duplicated inspection steps % of Atlantic municipalities using the acceptance framework Shortened inspection timelines for modular projects Fewer RFI (Requests for Information) from inspectors Improved manufacturer feedback on municipal acceptance | Regional | Map which inspections are already covered under CSA A277 (factory QA, structural, plumbing rough-ins, electrical pre-wiring, firestopping inside modules). List which inspections MUST remain on-site (foundation, hookups, sealing, fire separations, assembly). Review differences in inspection practices across Atlantic municipalities. Identify which assembly-stage checks commonly cause concern for inspectors. | PR | 9 | Concerns about duplicate inspections resulting in inefficiencies | Educate building inspectors on CSA A277 vs. CSA Z240 and develop regional inspection checklist for on site inspections (to be adopted by all AHJs). | - | - | - | - | Pending
PR10 | Policy and Regulatory | Inspections | NL | Service NL | Local manufacturers, NL Housing Corporation, CSA Group, modular installers | Provincial Government, Manufacturers | 2027 | Medium | 8 | Number of manufacturers receiving rebate Number of manufacturers getting CSA certification Increase in modular supply in NL | Provincial | Define the rebate criteria, including which manufacturers are eligible and what conditions must be met. Confirm which certification costs are eligible. Set up a simple application form so manufacturers can submit proof of certification to receive the rebate. | PR | 10 | Cost barriers and lack of incentives to becoming CSA certified. | Work with the Department of IET in NL to introduce a CSA A277 certification rebate. | Pending | Pending | Pending | Pending | -
PR11 | Policy and Regulatory | Inspections | NS | NS Department of Municipal Affairs & Housing - Building & Technical Standards Division NS Building Officials Association (NSBOA) | Municipal building officials, modular manufacturers supplying NS, general contractors & installation crews, Office of the Fire Marshal | Provincial Government, Municipal Government, Developers & General Contractors | 2026 | Easy | 9 | Number of inspectors using the checklist Reduction in duplicated full building reinspections | Local, provincial | Identify which assembly-stage checks commonly cause concern for inspectors. Draft a short checklist with NSBOA input. Map which inspections are already covered under CSA A277 (factory QA, structural, plumbing rough-ins, electrical pre-wiring, firestopping inside modules). List which inspections MUST remain on-site (foundation, hookups, sealing, fire separations, assembly). Review differences in inspection practices across Atlantic municipalities. | PR | 11 | Concerns that inspections done on components in factory instead of the whole building could lead to hidden issues which may emerge when components are combined. | Educate building inspectors on CSA A277 vs. CSA Z240 and develop regional inspection checklist for on site inspections (to be adopted by all AHJs). | Pending | Pending | Pending | Pending | -
PR12 | Policy and Regulatory | Permitting and Approvals | Atlantic Region | Municipal Building & Permitting Departments Provincial Housing Agencies Provincial Departments of Municipal Affairs | Manufacturers, developers, architects, engineers,permitting officials, general contractors. | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | 2027 | Medium | 9 | Average modular permitting time before vs. after track Number of repeatable modular designs pre-verified Increase in modular applications submitted | Local, provincial | Identify which modular designs can be pre-verified. Provide municipalities with CSA certification details. Update municipal workflows to skip factory-completed checks. | PR | 12 | Slow and costly approval processes | Building off the CMHC Housing Design Catalogue, create an Atlantic OSC catalogue and pre-approve permitting for projects designed to the catalogue. | Pending | Pending | Pending | Pending | -
PR13 | Policy and Regulatory | Permitting and Approvals | Atlantic Region | Municipal planning departments Provincial planning/technical standards divisions | Developers, modular manufacturers, development officers, municipal planners, building officials | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | 2026 | Easy | 9 | Improved clarity in pre-application reviews | Local, provincial, regional | Review existing zoning categories across sample municipalities. Identify where modular fits (e.g., single-unit, multi-unit, accessory). Validate with municipal planners and development officers. | PR | 13 | Municipal zoning rules restrict certain housing types, proximity requirements, or have unclear procedures between zoning and permitting steps. | Undertake a review of by-laws to minimize the impact on OSC designed buildings and increase housing supply in the municipality. | Pending | Pending | Pending | Pending | Pending
PR14 | Policy and Regulatory | Permitting and Approvals | Atlantic Region | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Municipal planners and development officers, building officials, modular manufacturers, developers, provincial housing agencies | Provincial Government, Municipal Government, Manufacturers, Developers & General Contractors | 2026 | Easy | 9 | Reduction in process-related RFIs for modular files | Local, provincial, regional | Review current approval steps across select municipalities. Define departmental roles and responsibilities clearly. Validate with municipal planners and building officials. | PR | 14 | Unclear processes: multiple layers of government or departments involved, unclear distinctions/responsibilities between codes, bylaws, and approval pathways. | Create and publish a guide and then digitize the processes provide clarity to individuals involved in the approval process and all builders looking to build in the municipality. | Pending | Pending | Pending | Pending | Pending
PR15 | Policy and Regulatory | Permitting and Approvals | NB | NB Department of Tourism, Heritage and Culture - Heritage Branch NB Department of Public Safety - Building Code Administration | Developers, municipalities planning staff, odular manufacturers, NB Housing, archaeology and heritage consultants | Provincial Government, Developers & General Contractors, Technical Professionals | 2026 | Easy | 7 | Reduction in unplanned heritage-related delays Fewer RFIs to the Heritage Branch | Provincial | Confirm which heritage triggers apply in unincorporated areas Summarize permit types (site alteration, impact assessment) Validate with NB Heritage Branch | PR | 15 | Heritage Conservation Act identifies heritage places in unincorporated areas, providing a barrier for housing. | Encourage the use of panelized (category 2) or other forms of OSC that can meet requirements within the Heritage Conservation Act. | Pending | Pending | Pending | Pending | -
TL1 | Transportation and Logistics | Module size and road restrictions | Atlantic Region | Provincial Departments of Transportation Municipal transportation departments | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026 | Medium | 9 | Number of agreements signed Reduced delays due to permit harmonization Number of municipalities participating | Local, provincial, regional | Regulatory coordination between provinces Legal framework for transport agreements | TL | 1 | Escort and permit rules for oversized modules (often >12 ft wide) differ between jurisdictions. | Collaborate across the region to develop overload escort/ permit requirements for both urban and rural centres to eliminate confusion across the sector. . | Pending | Pending | Pending | Pending | Pending
TL2 | Transportation and Logistics | Module size and road restrictions | Atlantic Region | Provincial Departments of Transportation & Infrastructure Municipal public works departments Utility companies Transportation/logistics providers | Utility companies (power, telecommunications, etc), provincial governments, municipal governments, transportation and logisitics providers, general contractors, owners | Transportation & Logistics Providers, Developers & General Contractors, Provincial Government, Municipal Government | 2026-2027 | Medium | 7 | Database completeness Reduced transport delays | Provincial, local | Data collection on bridges, roads, turning radii Mapping infrastructure conflicts | TL | 2 | Module width/height is constrained by bridge clearances, turning radii, and road widths | Consider design for manufacturing, transportation and assembly by province with the provinces transportation constraints in mind. | Pending | Pending | Pending | Pending | -
TL3 | Transportation and Logistics | Module size and road restrictions | Atlantic Region | Provincial Departments of Transportation Municipal permitting offices General contractors | General contractor, provincial governments | Provincial Government, Developers & General Contractors | 2026-2027 | Difficult | 8 | Number of deliveries adjusted around restrictions Reduced seasonal delays | Provincial | Schedule coordination with authorities Awareness of seasonal restriction periods | TL | 3 | Seasonal weight restrictions | Create designated transportation route with temporary staging yards for critical projects. | Pending | Pending | Pending | Pending | -
TL4 | Transportation and Logistics | Module size and road restrictions | NL | NL Department of Transportation amd Infrastructure NL Housing Corporation Industry associations Build Canada Homes | Industry associations, provincial government, municipal governments, federal government | Provincial Government, Industry Associations, Municipal Government, Federal Government | 2027 | Medium | 9 | Adoption of pre-approved designs Reduced transport delays | Local, regional, national | Gain a comprehensive understanding of NL-specific transportation requirements. | TL | 4 | Modules must be designed to match available island transport equipment. | Consider design for manufacturing, transportation and assembly with NL’s transportation constraints in mind. | - | - | - | - | Pending
TL5 | Transportation and Logistics | Module size and road restrictions | NL | NL Department of Transportation & Infrastructure Marine Atlantic | Provincial government, transportation and logistics providers | Provincial Government, Transportation & Logistics Providers | 2027 | Easy | 8 | Number of ferry trips using discounted/off-peak rates Cost savings On-time deliveries | Provincial | Agreements with ferry operators Approval of subsidy program | TL | 5 | Ferry costs add major expense for panelized construction. | Develop a pre-approved OSC route and work with ferry companies to provide discounted or off-peak ferry rates for projects carrying critical infrastructure (e.g., affordable housing). | Pending | Pending | Pending | Pending | -
TL6 | Transportation and Logistics | Module size and road restrictions | NB | New Brunswick Department of Transportation and Infrastructure (DTI) Logistics providers | Provincial government, transportation and logistics providers | Provincial Government, Transportation & Logistics Providers | 2027 | Difficult | 8 | Condition of delivery routes Reduced transport incidents Maintenance logs | Provincial | Identification of modular delivery routes Allocation of maintenance funding | TL | 6 | Poor detour roads increase delivery risk. | Work with NBDTI and local municipalities to consider OSC delivery on detour routes. | Pending | Pending | Pending | Pending | -
TL7 | Transportation and Logistics | Module size and road restrictions | NS | Nova Scotia Department of Public Works | Industry associations, provincial government, municipal governments, federal government | Industry Associations, Provincial Government, Municipal Government, Municipal Government | 2027 | Medium | 9 | Pre-approved design adoption Reduced transport-related issues | Local, regional, national | Development of standard modular dimensions Coordination with local authorities | TL | 7 | No standardized dimensions for local volumetric modular practice. | Provide discounted or off-peak ferry rates. | - | - | - | - | Pending
TL8 | Transportation and Logistics | Module size and road restrictions | NS | Nova Scotia Department of Public Works | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors | 2026 | Medium | 8 | Number of transport agreements signed Reduced permit delays | Local, provincial, regional | Provincial/regional coordination Legal framework established | TL | 8 | HRM has distinct escort/permit timing from rural NS. | Identify OSC delivery routes and infrastructure conflict-point database. | Pending | Pending | Pending | Pending | Pending
TL9 | Transportation and Logistics | Module size and road restrictions | NS | Nova Scotia Department of Public Works HRM Transportation and Public Workds Municipalities | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026-2027 | Medium | 9 | Number of pre-approved routes Reduced police escort requirements Transport time savings | Local, provincial | Mapping of routes Coordination with police and municipal authorities | TL | 9 | Larger modules require police escorts; delays occur when escorts leave | Collaborate across the region to develop overload escort/ permit requirements for both urban and rural centres to eliminate confusion across the sector. . | Pending | Pending | Pending | Pending | -
TL10 | Transportation and Logistics | Damage and Protection | Atlantic Region | Academic and training institutions CHBA | Manufacturers, transportation and logistics providers, general contractors, CHBA or construction associations(?), trades schools/colleges, academic institutions | Manufacturers, Transportation & Logistics Providers, Academic/Training Institutions, Industry Associations | 2027 | Medium | 8 | Reports of damage to modules during transportation Compliance with best practices | National | Review of current standards and practices. | TL | 10 | Inconsistent moisture barriers and wrapping practices. | Working with the UNB OCRC’s High-Performance Buildings Research (HPBR) Lab, identify best practices and for building envelope details and wrapping during transport. | - | - | - | - | -
TL11 | Transportation and Logistics | Damage and Protection | Atlantic Region | Industry associations Insurance companies | General contractors, manufacturers, owners, transportation and logistics providers | Industry Associations, Developers & General Contractors, Transportation & Logistics Providers, Manufacturers, Finance & Insurance/Business Services | 2026 | Easy | 7 | Reduction in disputes | Local | Identify common project conflicts | TL | 11 | Responsibility/liability for damage is unclear between manufacturer, hauler, GC. | Work with CCDC to create contract templates which identify roles and responsibilities of all parties and how project conflicts (module or panel damage) will be rectified. In parallel, work with the HPBR Lab on R&D to eliminate damages during transportation, erection and assembly | - | - | - | - | -
TL12 | Transportation and Logistics | Damage and Protection | Atlantic Region | Manufacturers Transportation/logistics providers CHBA National (framework for best practices) Trade schools/colleges (training) | Manufacturers, transportation and logistics providers, general contractors, CHBA or construction associations(?), trades schools/colleges, academic institutions | Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Academic/Training Institutions, Industry Associations | 2027 | Easy | 8 | Number of training sessions delivered Reports of damage to modules during transportation | National | Identify common project conflicts | TL | 12 | Denting, corner damage, and structural movement during loading/unloading. | Work with CCDC to create contract templates which identify roles and responsibilities of all parties and how project conflicts (module or panel damage) will be rectified. In parallel, work with the HPBR Lab on R&D to eliminate damages during transportation, erection and assembly. | - | - | - | - | -
TL13 | Transportation and Logistics | Damage and Protection | NS | Nova Scotia Department of Environment & Climate Change Natural Resources Canada (funding for low-impact equipment) | Provincial and federal governments, research institutions, industry groups | Provincial Government, Federal Government, Academic/Training Institutions, Industry Associations | 2027 | Medium | 8 | Reduction in soil compaction incidents Number of subsidized equipment purchases | National, regional | Identify qualified professionals to be an a OSC integrator. | TL | 13 | Heavy machinery causes soil compaction and clearing. | Identify an OSC integrator role in the project team to ensure proper planning and location of heavy equipment for transportation, erection and installation. | - | - | - | - | Pending
TL14 | Transportation and Logistics | Site access and Storage constraints | Atlantic Region | Municipal governments (zoning, temporary yard designation) Provincial Departments of Transportation (coordination) GC/transportation providers | General contractor, transportation/logistics provider, municipal governments, provincial governments, manufacturers, property owners | Municipal Government, Developers & General Contractors, Manufacturers, Transportation & Logistics Providers, Provincial Government | 2026 | Difficult | 8 | Number of staging yards designated Reduction in delivery delays Improvement in on-time module deliveries | Local, provincial | Database of land potentiall available for staging near sites | TL | 14 | Limited staging and storage space near construction sites. | Create designated temporary staging yards and use digital tools. | Pending | Pending | Pending | Pending | -
TL15 | Transportation and Logistics | Site access and Storage constraints | NB | New Brunswick Office of the Fire Marshal NB Department of Transportation & Infrastructure | Utility companies (power, telecommunications, etc), provincial governments, municipal governments, transportation and logisitics providers, general contractors, owners | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026-2027 | Medium | 7 | Number of conflicts identified in database Reduction in transport delays due to conflicts | Local, provincial | Database of infrastructure conflict points developed | TL | 15 | Conflicts with power lines, telecommunications, and fire marshal requirements. | Maintain conflict-point databases and use alternate construction methods. | Pending | Pending | Pending | Pending | -
TL16 | Transportation and Logistics | Site access and Storage constraints | NS | Halifax Regional Municipality (HRM) | General contractor, transportation/logistics provider, municipal government, manufacturer | Municipal Government, Developers & General Contractors, Manufacturers | 2026 | Easy | 8 | Number of temporary road closures approved Number of nighttime deliveries completed safely | Local | Owners, GCs, and manufacturers must be adaptable to the methods of construction most suitable for specific cases | TL | 16 | Difficult access in dense urban areas (tight roads, overhead utilities). | Create designated transportation route with temporary staging yards for critical projects. | - | - | - | - | -
WD1 | Skilled Workforce and Development | Training & Skills Development | Atlantic Region | Provincial departments of advanced education Trade schools/colleges (NSCC, NBCC, Holland College, CNA) | Industry groups, trades schools/colleges, provincial government | Provincial Government, Industry Associations, Academic/Training Institutions, | 2027 | Easy | 8 | Number of participants completing mini-courses Number of certificates issued Employer satisfaction with trained workforce | Regional | Secure industry/trade school partnerships Develop modular course content and materials | WD | 1 | Few OSC-specific training programs across colleges/trade schools. | Work collaboratively across the Atlantic provinces (UNB OCRC, NBCC, CCNB, NSCC, Holland College and CAN) to update curriculum and integrate OSC training . | - | - | - | - | Pending
WD2 | Skilled Workforce and Development | Training & Skills Development | Atlantic Region | Provincial departments of advanced education Trade schools/colleges (NSCC, NBCC, Holland College, CNA) Industry associations | Industry groups, trades schools/colleges, provincial government | Provincial Government, Academic/Training Institutions, Industry Associations | 2026-2027 | Easy | 7 | Number of participants completing mini-courses Number of certificates issued Employer satisfaction with trained workforce | Regional | Assess knowledge gaps across the region. Develop the curriculum and learning targets for the courses. | WD | 2 | Retraining to shift workers from traditional methods to MMC. | Offer OSC mini-courses, micro-credentials, workshops or the AMC certificate across the region. | - | - | - | - | Pending
WD3 | Skilled Workforce and Development | Training & Skills Development | Atlantic Region | Canadian Home Builders’ Association (CHBA National) Provincial Apprenticeship Authorities (NS Apprenticeship, NB Apprenticeship, etc.) | Industry groups, trades schools/colleges | Industry Associations, Academic/Training Institutions | 2027 | Medium | 8 | Adoption rate of national curriculum by provinces Number of institutions offering courses Enrollment numbers | National, provincial | Align provincial apprenticeship bodies to recognize modular-specific credentials Establish CHBA alignment Approval by national training authorities Funding for curriculum development | WD | 3 | Lack of clear, unified training pathways or standards for OSC across Canada. | Build off the AMC certificate to develop a national OSC curriculum and align apprenticeships with OSC credentials. | Pending | Pending | Pending | Pending | -
WD4 | Skilled Workforce and Development | Training & Skills Development | NS | NSCC, Nova Scotia Department of Advanced Education Provincial marketing/communications offices | Trades schools/colleges | Academic/Training Institutions, Provincial Government | 2026 | Medium | 9 | Enrollment numbers in NSCC modular courses Campaign reach (social media, schools) Number of applications received | Local. provincial | Marketing campaign materials Coordination with NSCC and provincial education authorities | WD | 4 | NSCC programs closing due to low enrollment. | Opportunity to rethink programs targeting MMC training. | Pending | Pending | Pending | Pending | -
WD5 | Skilled Workforce and Development | Training & Skills Development | NS | Provincial Apprenticeship Authorities Indigenous organizations | Industry groups, trades schools/colleges, Indigenous organizations | Industry Associations, Indigenous & Community Organizations, Provincial Government, Academic/Training Institutions | 2026 | Medium | 8 | Number of foreign-trained workers completing recognition process Number of culturally appropriate programs delivered Participation by Indigenous students | Provincial, regional | Agreements with credentialing bodies Partnerships with Indigenous organizations Development of training content | WD | 5 | Barriers for foreign-trained workers to gain equivalency; limited culturally appropriate programs for Indigenous communities. | Create streamlined credential-recognition pathways for internationally trained workers and engage Indigenous communities to understand how to best overcome the barrier. | Pending | Pending | Pending | Pending | Pending
WD6 | Skilled Workforce and Development | Skilled Trades & Labour Availability | NB | New Brunswick Community College (NBCC) NB Department of Post-Secondary Education, Training, and Labour (PETL) Industry associations | Trades schools/colleges, industry groups | Provincial Government, Academic/Training Institutions, Industry Associations | 2027 | Easy | 8 | Number of apprenticeships created Program enrollment Industry placement rates | Regional | College/unions agreement Curriculum development Employer sponsorship secured | WD | 6 | Shortage of skilled trades needed for OSC construction (design, assembly, mass timber, mechanical/electrical, etc.). | Expand OSC-focused trade training, fast-track upskilling, and introduce industry-supported apprenticeships. | - | - | - | - | Pending
WD7 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Atlantic Region | Provincial Economic Development Departments Innovation, Science & Economic Development Canada Modular manufacturers Build Canada Homes | Provincial government, federal government, industry groups, Manufacturers | Provincial Government, Industry Associations, Manufacturers, Federal Government | 2026-2027 | Medium | 9 | Efficiency KPIs folllowing implementation of automation Output per worker Reduced labour bottlenecks | Local, regional | Investment in automation equipment Worker training on new technology | WD | 7 | Low overall workforce availability limits the ability to scale modular construction. | Invest in factory automation to increase supply and strengthen OSC recruitment. | - | - | - | - | Pending
WD8 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Atlantic Region | Provincial Departments of Economic Development & Labour Employment and Social Development Canada (ESDC) Modular manufacturers | Provincial government, federal government, manufacturers | Provincial Government, Manufacturers, Federal Government | 2027 | Difficult | 7 | Number of relocation/housing subsidies granted Change in labour availability at rural facilities | Regional, local | Provincial/federal funding approval Policy design for incentives | WD | 8 | Rural factory locations limit labour access and reduce available workforce pools. | Provide relocation incentives and additional benefits (e.g., housing) to grow the workforce. | - | - | - | - | Pending
WD9 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Atlantic Region | Provincial Departments of Transportation & Infrastructure Large transportation/logistics companies | Industry groups, transportation and logistics providers | Industry Associations, Transportation & Logistics Providers, Provincial Government | 2026 | Difficult | 8 | Counts of shared resources Project delays due to lack of resources | Regional | Coordination agreements between provinces Identification of regional capacity gaps | WD | 9 | Limited access to specialized equipment operators (e.g., cranes, certified operators). | Promote collaboration and include heavy equipment and crane operations in the outreach for opportunities in the industry. | - | - | - | - | Pending
WD10 | Skilled Workforce and Development | Skilled Trades & Labour Availability | NS | Provincial Construction Associations Modular manufacturers | Indusry groups, general contractors | Industry Associations, Manufacturers, Developers & General Contractors | 2026 | Easy | 8 | Attendance at forums Number of contractors completing training modules Feedback surveys | Regional | Development of training modules Industry association support | WD | 10 | Few contractors have OSC experience, limiting participation. | Facilitate knowledge sharing with conferences and training. | - | - | - | - | Pending
WD11 | Skilled Workforce and Development | Skilled Trades & Labour Availability | NB | Provincial Government | Municipal government, provincial government, federal government | Municipal Government, Provincial Government, Federal Government | 2027 | Medium | 9 | Number of municipal staff hired Permitting turnaround times Number of pre-approved designs adopted | Local, provincial | Budget approval Digital permitting system development Modular design approval templates | WD | 11 | Staff shortages in public offices (planning, permitting, fire inspection) delay projects. | Identify training (e.g., AMC certificate) for existing municipal staff, increase staffing, digitize processes (e.g., permitting), and adopt pre-approved OSC designs. | Pending | Pending | Pending | Pending | -
WD12 | Skilled Workforce and Development | Skilled Trades & Labour Availability | NL | NL government: Department of Municipal and Community Affairs College of the North Atlantic | Trades schools/colleges, industry groups | Academic/Training Institutions, Provincial Government, Industry Associations | 2027 | Medium | 9 | Number of inspectors trained Inspector certification rates Reduced inspection delays | Provincial, regional | Collaboration with industry associations Curriculum development for inspector training | WD | 12 | New building inspectors are inexperienced. | Develop modular-specific inspector training modules. | Pending | Pending | Pending | Pending | Pending
WD13 | Skilled Workforce and Development | Skilled Trades & Labour Availability | NS | Municipal governments Manufacturers | Manufacturers | Manufacturers, Municipal Government | 2026 | Easy | 6 | Compliance with noise scheduling Reduced labour downtime | Local | Development of optimized scheduling guidelines Coordination with local municipalities | WD | 13 | Noise and work-hour limits reduce labour availability. | Improve scheduling efficiency. | - | - | - | - | -
WD14 | Skilled Workforce and Development | Skilled Trades & Labour Availability | PEI | Construction Association of PEI PEI Ministry of Housing, Land and Communities | Industry groups, academic and training institutions | Provincial Government, Industry Associations, Academic/Training Institutions | 2026 | Easy | 8 | Number of training sessions hosted Number of attendees trained | Provincial | Workshop scheduling and content planning | WD | 14 | Lack of on-island OSC experts on off-site methods. | Partner with the trade associations, schools and universities to host expert training sessions and encourage collaboration. | Pending | Pending | Pending | Pending | -
WD15 | Skilled Workforce and Development | Awareness, Culture & Mindset | Atlantic Region | Provincial construction associations CHBA Atlantic Provincial Departments of Labour (for outreach funding) | Industry groups | Provincial Government, Industry Associations | 2026 | Easy | 8 | Attendance at OSC events Surveys on workforce perception of OSC Increased modular adoption | Regional, provincial | Identification of industry professionals to host events Event planning | WD | 15 | Workforce resistance to OSC due to lack of familiarity, fear of job loss, or cultural hesitation toward new methods. | Host OSC industry events (tours, seminars, etc.) targeting skilled trades to highlight OSC and associated benefits. | Pending | Pending | Pending | Pending | Pending
WD16 | Skilled Workforce and Development | Awareness, Culture & Mindset | Atlantic Region | Provincial Departments of Housing & Communications CHBA Atlantic / CMHC / Build Canada Homes Manufacturers | Industry groups, provincial government, federal governement, manufacturers | Provincial Government, Industry Associations, Manufacturers, Federal Government | 2026-2027 | Easy | 9 | Public awareness metrics (survey data) Number of facility open houses Participation in outreach | National, regional, provincial | Marketing strategy developed Local case studies collected Cooperation from manufacturers | WD | 16 | Low awareness and misconceptions about OSC quality, aesthetics, and durability. | Create a docuseries, launch an OSC awareness campaign, develop industry-wide marketing, and require outreach from publicly funded companies. | Pending | Pending | Pending | Pending | Pending
WD17 | Skilled Workforce and Development | Awareness, Culture & Mindset | Atlantic Region | Provincial Construction Associations Trade schools/colleges Modular manufacturers Provincial Departments of Labour | Industry groups, trades schools/colleges, manufacturers | Industry Associations, Industry Associations, Manufacturers, Academic/Training Institutions | 2026-2027 | Easy | 8 | Number of OSC events held Number of sponsorships awarded and recipient career paths Training integration into programs | Regional, provincial, maybe national | Event planning and secured funding for sponsorships | WD | 17 | Limited promotion of modular construction within the industry and workforce. | Work with trade schools and associations to host OSC events, sponsor trades, and integrate OSC into existing programs. | Pending | Pending | Pending | Pending | Pending
WD18 | Skilled Workforce and Development | Workforce Retention & Recruitment | Atlantic Region | Provincial Housing Departments Employment and Social Development Canada (ESDC) Modular manufacturers | Provincial government, federal government, industry groups, Manufacturers | Provincial Government, Manufacturers, Federal Government, Industry Associations | 2027 | Difficult | 9 | Worker retention rates Housing uptake Employment stability metrics | Local, regional | Policy approval for housing subsidies Government purchasing agreements finalized | WD | 18 | Workforce retention challenges due to high living costs, housing affordability, and job security concerns in the construction sector. | With a commitment to OSC through offtake agreements, OSC businesses can offer long-term year-round employment and should consider full health and dental and additional benefits (subsidized housing, healthy living allowance, etc.) | - | - | - | - | Pending
WD19 | Skilled Workforce and Development | Workforce Retention & Recruitment | Atlantic Region | Provincial Departments of Labour & Advanced Education Federal Women and Gender Equality Canada (WAGE) Trade schools/colleges Modular manufacturers | Municipal, provincial, federal governments, manufacturers, trades schools/colleges | Municipal Government, Provincial Government, Academic/Training Institutions, Manufacturers, Federal Government, Indigenous & Community Organizations | 2026-2027 | Medium | 9 | Scholarship uptake Mentorship participation Diversity metrics in workforce | Provincial, regional | Funding approval for scholarships Mentorship program structure | WD | 19 | Difficulty attracting youth, women, diverse groups, and newcomers to construction trades. | Highlight the benefits of OSC company employment (year-round shift work) and support with bursaries, scholarships, mentorships, and DEI training requirements. | Pending | Pending | Pending | Pending | Pending
WD20 | Skilled Workforce and Development | Workforce Retention & Recruitment | NB | NB Department of Post-Secondary Education, Training, and Labour (PETL) Wolastoqey and Mi'kmaq business organizations NBCC and training institutions Industry associations | Municipal, provincial, federal governments, manufacturers, trades schools/colleges | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | 2026-2027 | Easy | 8 | Number of Indigenous-owned businesses supported DEI training completion Workforce participation rates | Provincial, regional | Funding and program approval DEI curriculum developed | WD | 20 | Culturally inappropriate or unwelcoming workplaces limit participation from Indigenous peoples and underrepresented groups. | Work with Indigenous communities to identify initiatives to overcome this barrier. | Pending | Pending | Pending | Pending | Pending

## Sheet2
Pending
In progress
Complete/ In action
-
Regional